## Home
|  |  | SUMMARY | Updated: | 2018-11-14 | [1392 empty] | Nom-SAR/DT | [33 empty] | QR | [14 empty] | Posting-SAR or PR | [47 empty] | Posting-Comment Only | [61 empty] | Posting Comment & Ballot | [62 empty] | Final Ballot | [29 empty] | Present to BOT | [36 empty] | Filing / Post Approval Train
Tutorial Video (11 min)
|  |  | Click here to report errors or issues |  | Baseline/ |  | 2015 | [364 empty] | 2016 | [365 empty] | 2017 | [364 empty] | 2018 | [364 empty] | 2019 | [364 empty] | 2020 | [365 empty] | 2021
|  | HOME | DO NOT SORT (Filtering Ok) | Early/(Late) | Current | <future> | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | June | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec
Index | Update status | Project (Filter) | Deliverables (Filter) | Days (Filter) | (Filter) | Filter | time axis 2015-01-01 to 2021-12-31
1 | Red | 2007-06.2 - Phase 2 System Protection Coordination | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment. | 69 | Archive_Baseline
2 | Red | 2007-06.2 - Phase 2 System Protection Coordination | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment. | 69 | Archive_Current
3 | Red | 2009-02 - Real-time Reliability Monitoring and Analysis Capabilities | New IRO-018-1 and TOP-010-1 | -47 | Archive_Baseline
4 | Red | 2009-02 - Real-time Reliability Monitoring and Analysis Capabilities | New IRO-018-1 and TOP-010-1 | -47 | Archive_Current
5 | Red | 2010-14.2.1 - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-005 | -4 | Archive_Baseline
6 | Red | 2010-14.2.1 - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-005 | -4 | Archive_Current
7 | Red | 2010-14.2.1 - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | FAC-001 | -4 | Archive_Baseline
8 | Red | 2010-14.2.1 - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | FAC-001 | -4 | Archive_Current
9 | Red | 2010-14.2.1 - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-006 | -4 | Archive_Baseline
10 | Red | 2010-14.2.1 - Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | BAL-006 | -4 | Archive_Current
11 | Red | 2010-14.2.2 - Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | BAL-004 | -7 | Archive_Baseline
12 | Red | 2010-14.2.2 - Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | BAL-004 | -7 | Archive_Current
13 | Red | 2013-03 - Geomagnetic Disturbance Mitigation | TPL-007-2 | 123 | Archive_Baseline
14 | Red | 2013-03 - Geomagnetic Disturbance Mitigation | TPL-007-2 | 123 | Archive_Current
15 | Red | 2015-04 - Alignment of Terms | Report on process (Phase II Improvement Report) | 0 | Archive_Baseline
16 | Red | 2015-04 - Alignment of Terms | Report on process (Phase II Improvement Report) | 0 | Archive_Current
17 | Red | 2015-07 - Internal Communications Capabilities | COM-001-3 | -74 | Archive_Baseline
18 | Red | 2015-07 - Internal Communications Capabilities | COM-001-3 | -74 | Archive_Current
19 | Red | 2015-08 - Emergency Operations | EOP-005, EOP-006, and EOP-008 | -205 | Archive_Baseline
20 | Red | 2015-08 - Emergency Operations | EOP-005, EOP-006, and EOP-008 | -205 | Archive_Current
21 | Red | 2015-08 - Emergency Operations | EOP-004 | -155 | Archive_Baseline
22 | Red | 2015-08 - Emergency Operations | EOP-004 | -155 | Archive_Current
23 | Green | 2015-09 - Establish and Communicate System Operating Limits | CIP-014-3, FAC-003-5, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 | -228 | Baseline
24 | Green | 2015-09 - Establish and Communicate System Operating Limits | CIP-014-3, FAC-003-5, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 | -228 | Current
25 | Green | 2015-09 - Establish and Communicate System Operating Limits | IROL Stds. | 0 | Baseline
26 | Green | 2015-09 - Establish and Communicate System Operating Limits | IROL Stds. | 0 | N/A
27 | Green | 2015-10 - Single Points of Failure TPL-001 | TPL-001-5 | -276 | Baseline
28 | Green | 2015-10 - Single Points of Failure TPL-001 | TPL-001-5 | -276 | Current
29 | Red | 2015-INT-01 - Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Interpretation CIP-002-5.1 | -9 | Archive_Baseline
30 | Red | 2015-INT-01 - Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Interpretation CIP-002-5.1 | -9 | Archive_Current
31 | Red | 2015-INT-02 - Interpretation of CIP-007-5 for Foxguard Solutions | CIP-007-5 | 0 | Archive_Baseline
32 | Red | 2015-INT-02 - Interpretation of CIP-007-5 for Foxguard Solutions | CIP-007-5 | 0 | Archive_Current
33 | Red | 2015-INT-03 - Interpretation of TOP-002-2.1b for FMPP | TOP-002-2.1b | 0 | Archive_Baseline
34 | Red | 2015-INT-03 - Interpretation of TOP-002-2.1b for FMPP | TOP-002-2.1b | 0 | Archive_Current
35 | Red | 2016-01 - Modifications to TOP and IRO Standards | TOP/IRO Standards | 46 | Archive_Baseline
36 | Red | 2016-01 - Modifications to TOP and IRO Standards | TOP/IRO Standards | 46 | Archive_Current
37 | Red | 2016-02 - Modifications to CIP Standards | LERC Definition & CIP-003-7 | 27 | Archive_Baseline
38 | Red | 2016-02 - Modifications to CIP Standards | LERC Definition & CIP-003-7 | 27 | Archive_Current
39 | Red | 2016-02 - Modifications to CIP Standards | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition | -289 | Archive_Baseline
40 | Red | 2016-02 - Modifications to CIP Standards | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition | -289 | Archive_Current
41 | Green | 2016-02 - Modifications to CIP Standards | Address TO Control Centers Performing Transmission Operator (TOP) Obligations. | -465 | Baseline
42 | Green | 2016-02 - Modifications to CIP Standards | Address TO Control Centers Performing Transmission Operator (TOP) Obligations. | -465 | Current
43 | Green | 2016-02 - Modifications to CIP Standards | Address all remaining V5TAG issues: Cyber Asset and BES CA (BCA) definitions, Network and Externally Accessible Devices (ESP, ERC, IRA), Obligations, Virtualization, and CIP Exceptional Circumstances. | 0 | Baseline
44 | Green | 2016-02 - Modifications to CIP Standards | Address all remaining V5TAG issues: Cyber Asset and BES CA (BCA) definitions, Network and Externally Accessible Devices (ESP, ERC, IRA), Obligations, Virtualization, and CIP Exceptional Circumstances. | No schedule | N/A
45 | Green | 2016-02 - Modifications to CIP Standards | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive) | 0 | Baseline
46 | Green | 2016-02 - Modifications to CIP Standards | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive) | No schedule | N/A
47 | Red | 2016-EPR-01 - Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards | PER-003-1 and PER-004-2 | 0 | Archive_Baseline
48 | Red | 2016-EPR-01 - Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards | PER-003-1 and PER-004-2 | 0 | Archive_Current
49 | Red | 2016-EPR-02 - Enhanced Periodic Review of Voltage and Reactive Standards | VAR-001-4.1 & VAR-002-4 | 0 | Archive_Baseline
50 | Red | 2016-EPR-02 - Enhanced Periodic Review of Voltage and Reactive Standards | VAR-001-4.1 & VAR-002-4 | 0 | Archive_Current
51 | Red | 2016-03 - Cyber Security Supply Chain Management | New and revised Standard(s) | -20 | Archive_Baseline
52 | Red | 2016-03 - Cyber Security Supply Chain Management | New and revised Standard(s) | -20 | Archive_Current
53 | Red | 2016-04 - Modifications to PRC-025-1 | PRC-025-2 | 0 | Archive_Baseline
54 | Red | 2016-04 - Modifications to PRC-025-1 | PRC-025-2 | 0 | Archive_Current
55 | Green | 2017-01 - Modifications to BAL-003-1.1 | BAL-003-2 | 0 | Baseline
56 | Green | 2017-01 - Modifications to BAL-003-1.1 | BAL-003-2 | 0 | Proposed
57 | Red | 2017-02 - Modifications to Personnel Performance, Training, and Qualifications Standards | PER-003-2, retire PER-004-2 | 24 | Archive_Baseline
58 | Red | 2017-02 - Modifications to Personnel Performance, Training, and Qualifications Standards | PER-003-2, retire PER-004-2 | 24 | Archive_Current
59 | Green | 2017-03 - Periodic Review of FAC-008-3 Standard | PR Recommendations | 0 | Baseline
60 | Green | 2017-03 - Periodic Review of FAC-008-3 Standard | PR Recommendations | 0 | N/A
61 | Green | 2017-04 - Periodic Review of Interchange Scheduling and Coordination Standards | PR Recommendations | 0 | Baseline
62 | Green | 2017-04 - Periodic Review of Interchange Scheduling and Coordination Standards | PR Recommendations | 0 | N/A
63 | Green | 2017-05 - Periodic Review NUC-001-3 | PR Recommendations | 0 | Baseline
64 | Green | 2017-05 - Periodic Review NUC-001-3 | PR Recommendations | 0 | N/A
65 | Red | 2017-06 - Project 2017-06 Modifications to BAL-002-2 | BAL-002-3 | 0 | Archive_Baseline
66 | Red | 2017-06 - Project 2017-06 Modifications to BAL-002-2 | BAL-002-3 | 0 | Archive_Current
67 | Green | 2017-07 - Stds Alignment with Registration | Standards with PSE, IA, or LSE | 0 | Baseline
68 | Green | 2017-07 - Stds Alignment with Registration | Standards with PSE, IA, or LSE | 0 | Proposed
69 | Green | 2018-01 - Canadian-specific Revisions to TPL-007-2 | TPL-007-3 | 0 | Open-Baseline
70 | Green | 2018-01 - Canadian-specific Revisions to TPL-007-2 | TPL-007-3 | 0 | Proposed
71 | Green | 2018-02 - Modifications to CIP-008 Cyber Security Incident Reporting | CIP-008-6 | 0 | Open-Baseline
72 | Green | 2018-02 - Modifications to CIP-008 Cyber Security Incident Reporting | CIP-008-6 | 0 | Proposed
73 | Green | 2018-03 - Standards Efficiency Review - Phase I | Retirements Only | 0 | Baseline
74 | Green | 2018-03 - Standards Efficiency Review - Phase I | Retirements Only | 0 | Proposed
75 | Red | 2018-04 - PRC-024-2 and Inverter Based Resources | TBD | 0 | Open-Baseline
76 | Red | 2018-04 - PRC-024-2 and Inverter Based Resources | TBD | 0 | Open-Baseline
77 | Green | Standards Efficiency Review - Phase 1 | Retirement of various requirements | 0 | Baseline
78 | Green | Standards Efficiency Review - Phase 1 | Retirement of various requirements | 0 | N/A
Note on F3: Click for Note 6.
Note on E4: Date driven off Final Ballot date.
Note on B5: Data Freshness Indicator: Green < 14 days since update Yellow >= 15 days since update Red > 30 days since update
Note on D77: NOTE: THIS PROJECT HAS A COMPRESSED TIME LINE.

## Summary
Project | Project Name | Status | Comments | Deliverable | Deadline | Priority in RSDP, click to see applicable Footnote | P81 Req (2013) | Number of Directives | No. of Guidances (see Note 2) | Directionally consistent with IERP findings (See Note 5) | Developer | PMOS Liaison | Affected Standards | Last Updated
SUMMARY | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | (Sorting okay) | HOME
2013-03 | Geomagnetic Disturbance Mitigation | Archived | FERC issued Order No. 830 on September 22, 2016 approving TPL-007-1 and directing modifications. The SDT will develop revised or new requirements to enhance the benchmark GMD event used in GMD assessments, require collection of GMD data, and establish deadlines for GMD Corrective Action Plans and mitigation measures. Revisions must be filed by May 29, 2018. The SAR was accepted by the Standards Committee on March 15, 2017. The standard was adopted by the NERC Board at their November 2017 meeting and filed on January 22, 2018. | TPL-007-2 | 2018-05-29 | Footnote 8, High | N/A | 4 | N/A | N/A | Scott Barfield | Jennifer Sterling | TPL-007-1 | 2018-01-29
2015-08 | Emergency Operations | Archived | Presented to BOT February 2017, preparing the filing. | EOP-005, EOP-006, and EOP-008 | N/A | Medium | N/A | 1 | N/A | N/A | Laura Anderson | Ken Goldsmith | EOP-005, EOP-006, and EOP-008 | 2017-03-06
2015-08 | Emergency Operations | Archived | Presented to BOT February 2017, preparing the filing. | EOP-004 | N/A | Medium | N/A | 1 | N/A | N/A | Laura Anderson | Ken Goldsmith | EOP-004 | 2017-03-06
2015-09 | Establish and Communicate System Operating Limits | Working to Additional Ballot | The standards were posted for formal comment through October 17, 2018 (extended from the 9th). The SDT plans to meet with the CIP SDT in November 6-8 to coordinate alignment with CIP-002. | CIP-014-3, FAC-003-5, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010 | N/A | Footnote 7, Medium | N/A | N/A | N/A | N/A | Latrice Harkness & Darrel Richardson | Ken Lanehome | CIP-014-3, FAC-003-5, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026-1 and the retirement of FAC-010 | 2018-11-14
2015-09 | Establish and Communicate System Operating Limits | On Hold | The IROL portion of the project has been placed on hold pending additional information. | IROL Stds. | N/A | Medium | N/A | N/A | N/A | N/A | Al McMeekin | TBD - On Hold | TBD - On Hold | 2018-11-14
2015-10 | Single Points of Failure TPL-001 | Pending Regulatory Filing | The standard was posted through September 22, 2018 and was approved by industry with a 66.67% vote. The standard was adopted by the NERC Board of Trustees at its November 2018 meeting. Next step is to filing with regulatory authorities. | TPL-001-5 | N/A | Footnote 8, High | N/A | 2 directives at P40 & P89 (Click this link for FERC Order) | N/A | N/A | Latrice Harkness | Mark Pratt | TPL-001-4 | 2018-11-14
2015-INT-01 | Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | Archived | Interpretation passed. FERC Approved, RD docket. | Interpretation CIP-002-5.1 | N/A | Low | N/A | N/A | N/A | N/A | Al McMeekin | Brian Murphy and Andrew Gallo | CIP-002-5.1 | 2017-02-09
2016-01 | Modifications to TOP and IRO Standards | Archived | Preparing for final ballot in Dec 2016. NOPR issued June 18, 2015 (under previous project 2014-03). Final Rule issued November 19, 2015 with three directives with an associated 18 month regulatory filing deadline. The SC authorized posting at the June 2016 SC meeting. Standards passed additional ballot ending October 17 2016 and will be posted for final ballot early December 2016. | TOP/IRO Standards | FERC deadline of July 27, 2017 | High | N/A | N/A | N/A | N/A | Mark Olson | Rod Kinard | TOP/IRO Standards | 2016-12-13
2016-02 | Modifications to CIP Standards | Archived | Petition was filed on March 3, 2017 requesting approval. TD at Lows resulted in a balloted CIP-003-7(i), which was not captured in the dates. "(i)" was dropped in the BOT presentation and filing and the standard was filed as CIP-003-7 | LERC Definition & CIP-003-7 | Directive: March 31, 2017 (LERC only) (March 31 in SAR) | High | N/A | 1 | N/A | N/A | Al McMeekin | Ken Lanehome and Ash Mayfield | CIP-003-7 | 2017-04-11
2016-02 | Modifications to CIP Standards | Archived | CIP-012-1 was approved by industry and the NERC Board adopted the standard at its August 2018 meeting and filed with regulatory authorities on September 18, 2018. | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition | N/A | Footnote 8, High | N/A | 2 | N/A | N/A | Jordan Mallory | Ken Lanehome, Ash Mayfield, and Kirk Rosener | CIP-012-1 | 2018-09-24
2016-02 | Modifications to CIP Standards | Responding to Comment | The SDT will be meeting with the 2015-9 SOL SDT on November 6-8 to align the CIP-002 standard with the SOL work. | Address TO Control Centers Performing Transmission Operator (TOP) Obligations. | N/A | Footnote 8, High | N/A | N/A | N/A | N/A | Jordan Mallory | Ken Lanehome, Ash Mayfield, and Kirk Rosener | CIP-002-5.1a | 2018-11-14
2016-02 | Modifications to CIP Standards | Posted | The SDT will be posting for a 45-day informal comment period on November 2 through December 18, 2018. | Address all remaining V5TAG issues: Cyber Asset and BES CA (BCA) definitions, Network and Externally Accessible Devices (ESP, ERC, IRA), Obligations, Virtualization, and CIP Exceptional Circumstances. | N/A | Footnote 8, High | N/A | N/A | N/A | N/A | Jordan Mallory | Ken Lanehome, Ash Mayfield, and Kirk Rosener | CIP-005, CIP-007 and CIP-010 | 2018-11-14
2016-02 | Modifications to CIP Standards | Responding to Comment | The CIP-003 standard was posted for comment and initial ballot through October 9, 2018. The ballot passed at 90.06%. The drafting team will meet through November and December to respond to comments and to determine next steps. | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive) | N/A | Footnote 8, High | N/A | N/A | N/A | N/A | Jordan Mallory | Ken Lanehome, Ash Mayfield, and Kirk Rosener | CIP-003-7 | 2018-11-14
2016-03 | Cyber Security Supply Chain Management | Archived | The petition was filed on September 26, 2017. | New and revised Standard(s) | 2017-09-27 | Footnote 8, High | N/A | 1 | N/A | N/A | Mark Olson | Brenda Hampton | CIP-005-6, CIP-010-3, and CIP-013-1 | 2017-10-03
2016-04 | Modifications to PRC-025-1 | Archived | Providing the SC an update on a non-substantive correction (Vlowside to Vhighside) to the Guidelines and Technical Basis before filing. | New and revised Standard(s) | N/A | Footnote 9, Medium | N/A | N/A | N/A | Yes | Scott Barfield-McGinnis | Charles Yeung | PRC-025-1 | 2018-03-14
2016-EPR-01 | Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards | Archived | The team will be requesting the Standards Committee at the June 14, 2017 meeting to accept a SAR to revise a Standard and to activate Project 2017-02. | PER-003-1 and PER-004-2 | N/A | Medium | N/A | N/A | N/A | N/A | Darrel Richardson | Mike Brytowski | PER-003-1 and PER-004-2, but PER-001-0.2 was not evaluated due to retirement on April 17, 2017. | 2017-06-14
2016-EPR-02 | Enhanced Periodic Review of Voltage and Reactive Standards | Archived | The periodic review team (PRT) responded to industry comments that affirm the PRT's recommendations. The PRT maintained its initial recommendation that the standards are sufficient to protect reliablity and although some things could be cleaned up, the recommendation is to not open the standards for revisions (i.e., yellow rating). The PRT will present their recommendations for acceptance to the Standards Committee on June 14, 2017 and to re-affirm the two VAR standards. | VAR-001-4.1 & VAR-002-4 | N/A | Medium | N/A | N/A | N/A | N/A | Scott Barfield-McGinnis | Amy Casuscelli | VAR-001-4.1 & VAR-002-4 | 2017-06-14
2017-01 | Modifications to BAL-003-1.1 | Pending SC Action | The SDT held a conference call on October 19 to finalize documentation for authorization of a formal posting for comment and initial ballot to the SC at its November meeting. | BAL-003-2 | N/A | Footnote 8, Medium | N/A | N/A | N/A | N/A | Laura Anderson | Amy Casuscelli & Linda Lynch | BAL-003-1.1 | 2018-11-14
2017-02 | Modifications to Personnel Performance, Training, and Qualifications Standards | Archived | NERC filed a petition for approval of PER-003 on July 23, 2018. Project archived by PMOS on Spetmber 13, 2018. | PER-003-2, retire PER-004-2 | N/A | Footnote 8, Medium | N/A | N/A | N/A | N/A | Darrel Richardson | Mike Brytowski | PER-003-1 & PER-004-2 | 2018-09-13
2017-03 | Periodic Review of FAC-008-3 Standard | On Hold | The periodic review team delivered their review recommendation to the SC in March 2018. The recommendation is to reaffirm with an action to revise, but at a later time. No action will be taken or archiving of the PTS item until the Standards Efficiency Reviews are complete. | PR Recommendations | N/A | Footnote 9, Low (was Medium previously) | N/A | N/A | N/A | N/A | Al McMeekin | Mark Pratt | FAC-008-3 | 2018-11-14
2017-04 | Periodic Review of Interchange Scheduling and Coordination Standards | On Hold | The response to comments are complete. Comments were in favor of the recommendations being made by the team which is to retire one standard and drop terms which are unclear in the standards. Periodic Review of subset INT Standards will provide the Standards Efficiency Review Team (SER) (Gary Nolan is the contact person) with the initial recommendations of the INT periodic review team, as well as all associated documents this week. No future meetings or postings expected for now. Project 2017-04 will then be placed on hold pending Standards Efficiency Review team recommendations/findings. No recommendations have been made to the Standards Committee. | PR Recommendations | N/A | Footnote 9, Low (was Medium previously) | N/A | N/A | N/A | N/A | Laura Anderson | Charles Yeung | INT-004, INT-006, INT-009, and INT-010 | 2018-11-14
2017-05 | Periodic Review NUC-001-3 | On Hold | The review template 45-day posting for preliminary recommendations ended January 29, 2018. There is a meeting scheduled for March 19 to review industry comments and discuss the team’s final recommendation. Given the overwhelming industry support for the team’s Preliminary Recommendation (Yellow-Revise), they do not anticipate a change in the recommended “color” of the standard. The PRT recommends to reaffirm the standard and has placed the project on hold pending the Standards Efficiency Reivew outcomes. | PR Recommendations | N/A | Footnote 9, Low (was Medium previously) | N/A | N/A | N/A | N/A | Mat Bunch | Amy Casuscelli and Colby Bellville | NUC-001-3 | 2018-11-14
2017-06 | Project 2017-06 Modifications to BAL-002-2 | Archived | NERC filed a petition for approval on August 17, 2018. The project was archived by the PMOS on September 13, 2018. | BAL-002-3 | N/A | Footnote 8, Medium | N/A | N/A | N/A | N/A | Darrel Richardson | Ken Lanehome | BAL-002-2 | 2018-09-13
2017-07 | Stds Alignment with Registration | On Hold | The project is on a temporary hold for coordination with other projects (such as Standards Efficiency Review and CIP) because many of the requirements that address these functional entities, are being considered for retirement. The project is not as simple as just removing a requirement with PSE, IA or LSE. The removal of the requirement may create a gap that would need to be addressed by another functional entity such as Distribution Provider (DP) or Transmission Owner (TO). This project is not addressing a reliability issue and has a low priority in the RSDP; therefore, the project is in a holding pattern in the interim. | Standards with PSE, IA, or LSE | 0 | Footnote 9, Low | N/A | N/A | N/A | N/A | Laura Anderson | Mike Brytowski | Standards with PSE, IA, or LSE | 2018-11-14
2017-08 | Open - Available | Inactive | 0 | CIP-014-4 | 0 | 0 | 0 | 0 | 0 | 0 | Mat Bunch | 0 | 0 | 2017-07-17
2018-01 | Canadian-specific Revisions to TPL-007-2 | Posted | The team met in September to respond to stakeholder comments. The standard is posted for a 45-day initial comment period and initial ballot through November 15, 2018. | TPL-007-3 | N/A | Footnote 10, Medium | N/A | N/A | N/A | N/A | Mat Bunch | Charles Yeung | TPL-007-2 | 2018-11-14
2018-02 | Modifications to CIP-008 Cyber Security Incident Reporting | Posted | The abbreviated comment period and initial ballot ended on October 22, 2018. The ballot failed considerably at 20.02%. NOTE: The second posting is scheduled for November 14, 2018. The comment period and ballot period considerably shorter to be able to work toward the January 2019 deadline. | CIP-008-6 | 2019-01-19 | Footnote 10, High | N/A | Order No. 848 (1 Directive, 4 elements) | N/A | N/A | Alison Oswald | Colby Bellville & Amy Casuscelli | CIP-008-5 | 2018-11-14
2018-03 | Standards Efficiency Review - Phase I | Nominations | 0 | Retirements Only | 0 | N/A | N/A | N/A | N/A | N/A | Laura Anderson | Mark Pratt & Michael Brytowski | Various | 2018-11-14
2018-04 | PRC-024-2 and Inverter Based Resources | Inactive | The two SARs were presented to the SC on September 13, 2018. Both SARs were rejected by the SC due to other industry work that is underway. A rejection letter was sent to CAISO by the SC Chair on September 21, 2018. | TBD | 0 | N/A | N/A | N/A | N/A | N/A | TBD | TBD | PRC-024-2 | 2018-11-14
Standards Efficiency Review | Phase 1 | SAR | The Standards Authorization Request was posted through September 26, 2018. The drafting team will be having the kick-off meeting on November 6, 2018, see the NERC calendar for details. | Retirement of various requirements | N/A | N/A, not priorized in the RSDP | (Ops Plan) Amy Casuscelli & Charles Yeung | (RT Ops) Mike Brytowski | (LT Plan) Linda Lynch | N/A | Chris Larson | Mark Pratt & Michael Brytowski | See SAR (too many to list) | 2018-11-14
Note on O1: Data Freshness Indicator: Green < 14 days since update Yellow >= 15 days since update Red > 30 days since update

## Archive_Summary (hidden)
ARCHIVE SUMMARY |  | (Sorting okay) | [9 empty] | HOME
Project | Project Name | Status | Comments | Deliverable | Deadline | Priority in RSDP, click to see applicable Footnote | P81 Req (2013) | Number of Directives | No. of Guidances (see Note 2) | Directionally consistent with IERP findings (See Note 5) | Developer | PMOS Liaison
2007-06.2 | Phase 2 System Protection Coordination | Pending Regulatory Approval | The standard passed overwhelmingly along with the definitions. BOT adopted August 11, 2016 and filed with FERC on September 2, 2016. | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment. | NERC-imposed deadline of 12/31/2015 | N/A | 1 - Move PRC-001, R1 to Training | 6 | 1 | Yes - PRC-001-1.1(ii), R1 was noted as duplicative of TOP-006-2 R3, but TOP-006 was retired without addressing R1 under TOP/IRO in 2015. | Scott Barfield-McGinnis | Brenda Hampton
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | Pending Regulatory Approval | 0 | New IRO-018-1 and TOP-010-1 | N/A | N/A | N/A | 3 | N/A | N/A | Mark Olson | Jennifer Sterling
2010-14.2.1 | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Pending Regulatory Filing | Passed final ballot with 72% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016. | BAL-005 | N/A | N/A | N/A | N/A | 4 | N/A | Darrel Richardson | Ken Goldsmith
2010-14.2.1 | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Pending Regulatory Filing | Passed final ballot with 80% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016. | FAC-001 | N/A | N/A | 11 | 7 | 1 | N/A | Darrel Richardson | Ken Goldsmith
2010-14.2.1 | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001 | Pending Regulatory Filing | Passed final ballot with 94% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016. | BAL-006 | N/A | N/A | N/A | N/A | N/A | N/A | Darrel Richardson | Ken Goldsmith
2010-14.2.2 | Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2 | Pending Regulatory Approval | Filed with regulators on November 10, 2016. | BAL-004 | N/A | N/A | N/A | N/A | 4 | N/A | Darrel Richardson | Ken Goldsmith
2015-04 | Alignment of Terms | Other | SDT is developing recommendations to present to SC. The Phase II work was completed in February 2016 and the proposed recommendations were submitted for consideration at the March 2016 meeting. The item was pulled from the SC agenda based on a request from the SC chair, Brian Murphy. The SDT reviewed the revisions proposed by the SC chair, and determined to move forward with submitting the recommendations as developed by the SDT. The Phase II recommendation document will be resubmitted for inclusion on the September 2016 SC agenda. | Report on process (Phase II Improvement Report) | N/A | Low | N/A | N/A | N/A | N/A | Lacey Ourso | Andrew Gallo
2015-07 | Internal Communications Capabilities | Pending Regulatory Filing | Filing anticipated in late August. | COM-001-3 | N/A | High | N/A | 1 | N/A | N/A | Darrel Richardson | Brenda Hampton
2015-INT-02 | Interpretation of CIP-007-5 for Foxguard Solutions | Inactive | Currently on hold. SC approved RFI and for the interpretation drafting team to be formed in April 2016. | CIP-007-5 | N/A | N/A | N/A | N/A | N/A | N/A | Lacey Ourso | Brian Murphy
2015-INT-03 | Interpretation of TOP-002-2.1b for FMPP | Inactive | Currently on hold. Interpretation drafting team recommendations were submitted to the SC in February 2016. | TOP-002-2.1b | N/A | Low | N/A | N/A | N/A | N/A | Lacey Ourso | Brian Murphy
2016-02 | Modifications to CIP Standards | Archived | Petition was filed on March 3, 2017 requesting approval. TD at Lows resulted in a balloted CIP-003-7(i), which was not captured in the dates. "(i)" was dropped in the BOT presentation and filing and the standard was filed as CIP-003-7 | LERC Definition & CIP-003-7 | Directive: March 31, 2017 (LERC only) (March 31 in SAR) | High | N/A | 1 | N/A | N/A | Al McMeekin | Ken Lanehome and Ash Mayfield

## 2007-06.2 (hidden)
Project | 2007-06.2 | [5 empty] | Home
Project Name | Phase 2 System Protection Coordination
Status | Pending Regulatory Approval
Comments | The standard passed overwhelmingly along with the definitions. BOT adopted August 11, 2016 and filed with FERC on September 2, 2016.
Deliverable | PRC-001-1.1.(Ret), PER-006-1 (New), and revision to definitions of Operational Planning Analysis and Real-time Assessment.
Deadline | NERC-imposed deadline of 12/31/2015
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | 1 - Move PRC-001, R1 to Training
Number of Directives | 6
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5) | Yes - PRC-001-1.1(ii), R1 was noted as duplicative of TOP-006-2 R3, but TOP-006 was retired without addressing R1 under TOP/IRO in 2015.
Developer | Scott Barfield-McGinnis
PMOS Liaison | Brenda Hampton
Affected Standards | PRC-001-1.1.(ret.), PER-006-1 (new)
Last Updated | 2016-09-29
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  | 0 | 0 |  |  | 1
Nominations - DT | 2015-01-06 | 2015-01-20 | 2015-01-30 | 2015-02-13 | 24 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2007-06-11 | 2007-07-10 | 2007-06-11 | 2007-07-10 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  | 0 | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  | 0 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  | 0 | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-07-29 | 2015-09-11 | 2015-05-11 | 2015-06-25 | -79 | Regulatory Meeting | 62.55% | 8
CAB - Com/Add Ballot 2 | 2015-10-06 | 2015-11-19 | 2015-07-27 | 2015-09-10 | -71 | Baseline Reset | 57.29% | 9
CAB - Com/Add Ballot 3 | 2016-03-10 | 2016-04-30 | 2016-02-14 | 2016-03-30 | -25 | Change in Approach | 80.57% | 10
CAB - Com/Add Ballot 4 |  |  | 2016-06-01 | 2016-07-16 | 0 | Not needed |  | 11
CAB - Com/Add Ballot 5 |  |  |  | 0 | 0 |  |  | 12
FB - Final Ballot | 2016-05-17 | 2016-05-26 | 2016-07-25 | 2016-08-04 | 69 |  | 82.52% | 13
PTB - Present to BOT | 2016-08-10 | 2016-08-12 | 2016-08-10 | 2016-08-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-09-10 | 2016-10-10 | 2016-09-10 | 2016-10-10 | 0 |  |  | 15
PT - Post Approval Training |  |  |  | 0 | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain the delay | 2015-05-01 | Did not pass Septmber 2015 ballot and will plan to conduct another SDT meeting and post for additional ballot. Goal to post end of January 2016; however, the SDT's plan to present a PER-005-2 revision met industry opposition during informal outreach. The SDT held a technical conference to resolve - resulting in PER-006-1 and definition changes to OPA and RTA. The first formal comment period for PER-006-1 runs March 10 to April 25 with an initial ballot.
Explain early finish | 2016-06-01 | PER-006-1 did not require an additional planned ballot, passed on initial.

## 2009-02 (hidden)
Project | 2009-02 | [5 empty] | Home
Project Name | Real-time Reliability Monitoring and Analysis Capabilities
Status | Pending Regulatory Approval
Comments
Deliverable | New IRO-018-1 and TOP-010-1
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | High
P81 Req (2013) | N/A
Number of Directives | 3
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mark Olson
PMOS Liaison | Jennifer Sterling
Affected Standards | None
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-07-16 | 2015-08-17 | 2015-04-01 | 2015-05-01 | -106 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-09-24 | 2015-11-09 | 2015-06-15 | 2015-07-30 | -101 |  | 47.38% & 48.00% | 8
CAB - Com/Add Ballot 2 | 2015-12-10 | 2016-01-26 | 2015-08-15 | 2015-09-29 | -117 |  | 72.13% & 68.01% | 9
CAB - Com/Add Ballot 3 |  |  | 2015-11-01 | 2015-12-16 | 0 | Not needed |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-02-17 | 2016-02-26 | 2016-01-01 | 2016-01-11 | -47 |  | 75.68% & 73.87% | 13
PTB - Present to BOT | 2016-05-04 | 2016-05-05 | 2016-02-10 | 2016-02-11 | -84 |  |  | 14
Filing - Filing with Regulators | 2016-05-26 | 2016-06-15 | 2016-06-01 | 2016-06-15 | 6 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive | 2016-06-14 | Moved to archives at PMOS meeting 6/14/2016.

## 2010-14.2.1a (hidden)
Project | 2010-14.2.1 | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001
Status | Pending Regulatory Filing
Comments | Passed final ballot with 72% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016.
Deliverable | BAL-005
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | BAL-005
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-07-16 | 2014-08-15 | 2014-07-16 | 2014-08-15 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-07-30 | 2015-09-14 | 2015-11-20 | 2016-01-04 | 113 |  | 55.97% | 8
CAB - Com/Add Ballot 2 | 2015-11-10 | 2016-01-11 |  |  | -42318 |  | 70.64% | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 | 2016-01-25 | 2016-02-04 | -4 |  | 72.06% | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-02-10 | 2016-02-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-04-20 | 2016-05-20 | 2016-04-20 | 2016-05-20 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-05-01 | Going to final ballot end of January 2016 and planned for presentation at February 2016 Board meeting.

## 2010-14.2.1b (hidden)
Project | 2010-14.2.1 | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001
Status | Pending Regulatory Filing
Comments | Passed final ballot with 80% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016.
Deliverable | FAC-001
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | 11
Number of Directives | 7
No. of Guidances (see Note 2) | 1
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | FAC-001
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-07-16 | 2014-08-14 | 2014-07-16 | 2014-08-14 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-11-10 | 2016-01-11 | 2015-11-20 | 2016-01-04 | 10 |  | 75.54% | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 | 2016-01-25 | 2016-02-04 | -4 |  | 80.15% | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-02-10 | 2016-02-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-04-20 | 2016-05-20 | 2016-04-20 | 2016-05-20 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes

## 2010-14.2.1c (hidden)
Project | 2010-14.2.1 | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls – BAL-005, BAL-006, FAC-001
Status | Pending Regulatory Filing
Comments | Passed final ballot with 94% approval February 2016. Adopted by NERC BOT in February 2016. Filed with FERC in April 2016.
Deliverable | BAL-006
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | BAL-006
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2014-07-16 | 2014-08-14 | 2014-07-16 | 2014-08-14 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-11-10 | 2016-01-11 | 2015-11-20 | 2016-01-04 | 10 |  | 94.3% | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-01-29 | 2016-02-08 | 2016-01-25 | 2016-02-04 | -4 |  | 94.61% | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-02-10 | 2016-02-12 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-04-20 | 2016-05-20 | 2016-04-20 | 2016-05-20 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-05-01 | Going to final ballot end of January 2016 and planned for presentation at February 2016 Board meeting.

## 2010-14.2.2 (hidden)
Project | 2010-14.2.2 | [5 empty] | Home
Project Name | Phase 2 of Balancing Authority Reliability-based Controls - BAL-004-2
Status | Pending Regulatory Approval
Comments | Filed with regulators on November 10, 2016.
Deliverable | BAL-004
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | 4
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Goldsmith
Affected Standards | BAL-004
Last Updated | 2016-12-13
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-03-17 | 2015-04-15 | 2015-01-15 | 2015-02-14 | -61 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2015-08-12 | 2015-08-25 | 2015-04-01 | 2015-05-01 | -133 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-09-24 | 2015-11-12 | 2015-10-01 | 2015-11-15 | 7 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2015-12-08 | 2015-12-17 | 2015-12-01 | 2015-12-11 | -7 |  |  | 13
PTB - Present to BOT | 2016-02-10 | 2016-02-12 | 2016-05-01 | 2016-05-03 | 81 |  |  | 14
Filing - Filing with Regulators | 2016-11-10 | 2016-11-13 | 2016-06-01 | 2016-06-11 | -162 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive Projectg | 2016-12-13 | Directed to archive at December 13, 2016 PMOS Meeting.

## 2013-03 (hidden)
Project | 2013-03 | [5 empty] | Home
Project Name | Geomagnetic Disturbance Mitigation
Status | Archived
Comments | FERC issued Order No. 830 on September 22, 2016 approving TPL-007-1 and directing modifications. The SDT will develop revised or new requirements to enhance the benchmark GMD event used in GMD assessments, require collection of GMD data, and establish deadlines for GMD Corrective Action Plans and mitigation measures. Revisions must be filed by May 29, 2018. The SAR was accepted by the Standards Committee on March 15, 2017. The standard was adopted by the NERC Board at their November 2017 meeting and filed on January 22, 2018.
Deliverable | TPL-007-2
Deadline | 2018-05-29
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | 4
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Scott Barfield
PMOS Liaison | Jennifer Sterling
Affected Standards | TPL-007-1
Last Updated | 2018-01-29
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-10-20 | 2016-11-09 | 2016-10-20 | 2016-11-09 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-12-16 | 2017-01-20 | 2016-12-20 | 2017-01-19 | 4 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-06-28 | 2017-08-11 | 2017-06-15 | 2017-07-30 | -13 |  | Passed | 8
CAB - Com/Add Ballot 2 |  |  | 2017-09-11 | 2017-10-26 | 0 |  | Changed from 9/11 to 9/22 to stagger 2013-03, 2015-09, and 2015-10. | 9
CAB - Com/Add Ballot 3 |  |  | 2017-11-29 | 2018-01-13 | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2017-10-20 | 2017-10-30 | 2018-02-20 | 2018-03-02 | 123 |  | Passed | 13
PTB - Present to BOT | 2017-11-07 | 2017-11-09 | 2018-05-01 | 2018-05-03 | 175 |  | Adopted | 14
Filing - Filing with Regulators | 2017-12-07 | 2017-12-10 | 2018-05-26 | 2018-05-29 | 170 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
No dates provided | 2016-06-01 | Project finished prior to 2015.
Accept Baseline Schedule | 2017-06-14 | Accepted by unamious consent.
Schedule Adjustment | 2017-08-10 | Changed from 9/11 to 9/22 to stagger 2013-03, 2015-09, and 2015-10.
Archive Project | 2018-01-31 | PMOS archived the project now that it is complete.

## 2015-04 (hidden)
Project | 2015-04 | [5 empty] | Home
Project Name | Alignment of Terms
Status | Other
Comments | SDT is developing recommendations to present to SC. The Phase II work was completed in February 2016 and the proposed recommendations were submitted for consideration at the March 2016 meeting. The item was pulled from the SC agenda based on a request from the SC chair, Brian Murphy. The SDT reviewed the revisions proposed by the SC chair, and determined to move forward with submitting the recommendations as developed by the SDT. The Phase II recommendation document will be resubmitted for inclusion on the September 2016 SC agenda.
Deliverable | Report on process (Phase II Improvement Report)
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Low
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Lacey Ourso
PMOS Liaison | Andrew Gallo
Affected Standards | Glossary/ROP
Last Updated | 2016-10-04
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive | 2017-01-26 | By PMOS action

## 2015-07 (hidden)
Project | 2015-07 | [5 empty] | Home
Project Name | Internal Communications Capabilities
Status | Pending Regulatory Filing
Comments | Filing anticipated in late August.
Deliverable | COM-001-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | High
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Brenda Hampton
Affected Standards | COM-001-3
Last Updated | 2016-10-04
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2015-06-11 | 2015-06-24 | 2015-06-01 | 2015-06-15 | -10 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-06-11 | 2015-07-11 | 2015-06-01 | 2015-07-01 | -10 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2015-09-25 | 2015-11-16 | 2015-07-15 | 2015-08-29 | -72 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-03-23 | 2016-05-09 | 2015-10-01 | 2015-11-15 | -174 |  |  | 9
CAB - Com/Add Ballot 3 |  |  | 2016-01-01 | 2016-02-15 | 0 | Not needed |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-06-14 | 2016-06-24 | 2016-04-01 | 2016-04-11 | -74 |  | 83.25% | 13
PTB - Present to BOT | 2016-08-10 | 2016-08-12 | 2016-05-06 | 2016-05-08 | -96 |  |  | 14
Filing - Filing with Regulators | 2016-08-10 | 2016-08-12 | 2016-08-10 | 2016-08-12 | 0 |  |  | 15
PT - Post Approval Training | 2016-09-10 | 2016-10-10 | 2016-09-10 | 2016-10-10 | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Update to SC | 2016-06-15 | Update given to SC concerning delay.
Archived | 2016-12-01 | Project is complete.

## 2015-08a (hidden)
Project | 2015-08 | [5 empty] | Home
Project Name | Emergency Operations
Status | Archived
Comments | Presented to BOT February 2017, preparing the filing.
Deliverable | EOP-005, EOP-006, and EOP-008
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Ken Goldsmith
Affected Standards | EOP-005, EOP-006, and EOP-008
Last Updated | 2017-03-06
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-06-14 | 2016-06-27 | 2016-01-11 | 2016-01-21 | -155 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-07-21 | 2015-08-19 | 2015-07-15 | 2015-08-14 | -6 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-06-29 | 2016-08-12 | 2016-01-25 | 2016-03-10 | -156 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-10-26 | 2016-12-09 | 2016-04-04 | 2016-05-19 | -205 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-12-28 | 2017-01-06 | 2016-06-06 | 2016-06-16 | -205 |  | 83.65% (EOP-005) & 80.56% (EOP-006) | 13
PTB - Present to BOT | 2017-02-08 | 2017-02-10 | 2016-08-08 | 2016-08-10 | -184 |  |  | 14
Filing - Filing with Regulators | 2017-03-10 | 2017-03-15 | 2016-09-07 | 2016-09-12 | -184 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-06-06 | The SDT slowed development.
Archived | 2017-03-15 | PMOS WECC Meeting

## 2015-08b (hidden)
Project | 2015-08 | [5 empty] | Home
Project Name | Emergency Operations
Status | Archived
Comments | Presented to BOT February 2017, preparing the filing.
Deliverable | EOP-004
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Ken Goldsmith
Affected Standards | EOP-004
Last Updated | 2017-03-06
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-07-14 | 2016-07-28 | 2016-04-08 | 2016-04-18 | -97 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-07-21 | 2015-08-19 | 2015-07-15 | 2015-08-14 | -6 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-07-25 | 2016-09-08 | 2016-04-18 | 2016-06-02 | -98 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-11-18 | 2017-01-06 | 2016-06-27 | 2016-08-11 | -144 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2017-01-24 | 2017-02-02 | 2016-08-22 | 2016-09-01 | -155 |  |  | 13
PTB - Present to BOT | 2017-02-08 | 2017-02-10 | 2016-10-31 | 2016-11-02 | -100 |  |  | 14
Filing - Filing with Regulators | 2017-03-10 | 2017-03-15 | 2016-11-30 | 2016-12-05 | -100 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay in project | 2016-05-01 | The delay was to reduce industry burden by simplifying the event reporting process such that a single form and submission system satisfies both EOP-004 and the U.S. Department of Energy’s reporting requirements, the Project 2015-08 EOP SDT is collaborating with the U.S. Department of Energy to harmonize reporting requirements/reports. This collaboration has changed the project schedule for EOP-004. The project’s PMOS representative, Ken Goldsmith, supports this project timeline change.
Archived | 2017-03-15 | PMOS WECC meeting.

## SER_Ph1
Project | Standards Efficiency Review | [5 empty] | Home
Project Name | Phase 1
Status | SAR
Comments | The Standards Authorization Request was posted through September 26, 2018. The drafting team will be having the kick-off meeting on November 6, 2018, see the NERC calendar for details.
Deliverable | Retirement of various requirements
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A, not priorized in the RSDP
Operations Planning Subteam | (Ops Plan) Amy Casuscelli & Charles Yeung
Real-time Operations Subteam | (RT Ops) Mike Brytowski
Long-term Planning Subteam | (LT Plan) Linda Lynch
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Chris Larson
Primary PMOS Liaison(s) | Mark Pratt & Michael Brytowski
Affected Standards | See SAR (too many to list)
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-11-14 | 2017-11-30 | [5 empty] | 1
Nominations - DT | 2018-08-28 | 2018-09-17 | [5 empty] | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-08-28 | 2018-09-26 | [5 empty] | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2018-06-07 | 2018-07-10 | [5 empty] | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes

## 2015-09
Project | 2015-09 | [5 empty] | Home
Project Name | Establish and Communicate System Operating Limits
Status | Working to Additional Ballot
Comments | The standards were posted for formal comment through October 17, 2018 (extended from the 9th). The SDT plans to meet with the CIP SDT in November 6-8 to coordinate alignment with CIP-002.
Deliverable | CIP-014-3, FAC-003-5, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026 and the retirement of FAC-010
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 7, Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Latrice Harkness & Darrel Richardson
PMOS Liaison | Ken Lanehome
Affected Standards | CIP-014-3, FAC-003-5, FAC-013-3, PRC-002-3, PRC-023-5, PRC-026-1 and the retirement of FAC-010
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  | 2016-04-04 | 2016-04-14 | 0 | Not needed |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-08-20 | 2015-09-21 | 2015-08-20 | 2015-09-21 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2016-07-14 | 2016-08-12 | 2016-07-08 | 2016-08-07 | -6 |  |  | 6
CP2 - Comment Period 2 | [7 empty] | 7
CIB - Com/Ballot 1 (Initial) | 2017-09-29 | 2017-11-13 | 2017-09-22 | 2017-11-05 | -7 |  | Posting date changed see notes 8/10 and 8/25. | 8
CAB - Com/Add Ballot 2 | 2018-04-09 | 2018-05-24 | 2018-01-17 | 2018-03-02 | -82 |  |  | 9
CAB - Com/Add Ballot 3 | 2018-08-24 | 2018-10-17 |  |  |  |  | not in original baseline | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-11-16 | 2018-11-26 | 2018-04-02 | 2018-04-12 | -228 |  |  | 13
PTB - Present to BOT | 2018-11-15 | 2018-11-17 | 2018-05-01 | 2018-05-03 | -198 |  |  | 14
Filing - Filing with Regulators | 2018-12-15 | 2018-12-18 | 2018-06-01 | 2018-06-04 | -197 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Explain delay | 2016-05-01 | The apparent delay in the project is due to missing an earlier update to the PMOS Annual Project Calendar. Baseline Schedule has not been adjusted.
Developer change | 2017-01-13 | Transition from Lacey Ourso to Darrel Richardson.
Developer change | 2017-04-01 | Added Al McMeekin to the project.
Added SDT schedule | 2017-07-20 | Updated initial, additional, final, BOT, and filing projected dates.
Schedule Adjustment | 2017-08-10 | Changed from 9/7 to 9/12 to stagger 2013-03, 2015-09, 2015-10, and 2016-02c.
Accept Baseline Realignment | 2017-08-10 | The project baseline was over a year behind (454 days as measured by the planned final ballot) in the original schedule due to developing additional information in support of the team's approach. The team also split off the IROL portion of the project. Whether this will be a 2015-09b, 2015-09.1, or a new project is yet to be determined.
Schedule Adjustment | 2017-08-25 | The SOL team needed additional time to complete reviews of whitepapers; therefore, adjusted their schedule from 9/12 as accepted by the PMOS on August 10 to 9/30. The change does not impact their December team meeting plans.
Informal definition posting | 2017-09-29 | The informal posting of the definitions is not reflected in the above dates grid.
Developer change | 2018-03-01 | Al McMeeking and Darrel Richardson were replaced by Katherin Street.
Developer change | 2018-04-25 | Katherin Street was replaced by Darrel Richardson.
Updated Proposed Schedule | 2018-06-21 | Project going to 3rd ballot week of 7/16/2018, adjusted final ballot, BOT, and filing accordingly.
Standards added | 2018-07-10 | Added CIP-014-3 FAC-003-5, FAC-013-3, PRC-023-5, and PRC-026-2 to affected and deliverable standards.
Developer change | 2018-10-30 | Latrice Harkness will be assuming the developer role from Darrel as he is working in a different area now.

## 2015-09b
Project | 2015-09 | [5 empty] | Home
Project Name | Establish and Communicate System Operating Limits
Status | On Hold
Comments | The IROL portion of the project has been placed on hold pending additional information.
Deliverable | IROL Stds.
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Al McMeekin
PMOS Liaison | TBD - On Hold
Affected Standards | TBD - On Hold
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Bifurcate Project | 2017-03-31 | Split the IRO portion into this section for tracking.
Worksheet created | 2017-08-10 | PMOS suggested visibility on this IROL portion.
Worksheet made visible | 2018-04-25 | PMOS requested that the IRO portion be tracked going forward.

## 2015-10
Project | 2015-10 | [5 empty] | Home
Project Name | Single Points of Failure TPL-001
Status | Pending Regulatory Filing
Comments | The standard was posted through September 22, 2018 and was approved by industry with a 66.67% vote. The standard was adopted by the NERC Board of Trustees at its November 2018 meeting. Next step is to filing with regulatory authorities.
Deliverable | TPL-001-5
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | 2 directives at P40 & P89 (Click this link for FERC Order)
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Latrice Harkness
PMOS Liaison | Mark Pratt
Affected Standards | TPL-001-4
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2015-11-12 | 2015-12-01 | 2016-01-18 | 2016-02-01 | 67 |  |  | 1
Nominations - DT | 2016-07-22 | 2016-08-05 | 2016-07-25 | 2016-08-08 | 3 |  |  | 2
QR - Quality Review |  |  | 2016-05-30 | 2016-06-09 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2015-11-12 | 2015-12-17 | 2015-11-12 | 2015-12-17 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2016-05-26 | 2016-06-24 | 2016-06-15 | 2016-07-15 | 20 | Expanded Scope |  | 5
CP1 - Comment Period 1 | 2017-04-25 | 2017-05-24 | 2017-04-25 | 2017-05-24 | 0 | Other | Team added informal comment period | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-09-08 | 2017-10-23 | 2017-07-05 | 2017-08-18 | -65 |  | Held at 9/7 to stagger 2013-03 and 2015-09. | 8
CAB - Com/Add Ballot 2 | 2018-02-23 | 2018-04-23 | 2017-10-18 | 2017-12-01 | -128 |  | Period extended from 4/9 to 4/23 due to changes | 9
CAB - Com/Add Ballot 3 | 2018-07-30 | 2018-09-14 |  |  |  |  | Additional period | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-10-11 | 2018-10-22 | 2018-01-08 | 2018-01-17 | -276 |  |  | 13
PTB - Present to BOT | 2018-11-06 | 2018-11-08 | 2018-02-01 | 2018-02-03 | -278 |  |  | 14
Filing - Filing with Regulators | 2018-12-06 | 2018-12-09 | 2018-03-01 | 2018-03-04 | -280 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Expansion of Scope | 2016-06-14 | FERC directives added (P40 & P89) additional scoping in addition to industry comments following the second SAR posting. The MOD references are being updated due to some retiring in July 2016.
Developer change | 2017-01-13 | Transition from Lacey Ourso to Soo Jin Kim until a new developer is assigned.
Accept Schedule | 2017-04-27 | Accepted by PMOS.
Schedule deviation | 2017-06-13 | Baseline initial ballot of 7/5/2017 moved to 9/7/2017 due addressing comments and scope of SAR. Schedule accounts for SC not meeting in August.
Schedule Adjustment | 2017-08-10 | No adjustment required 2013-03, 2015-09, and 2016-02 were staggered to spread postings out.
Schedule Adjustment | 2018-09-13 | PMOS agreed to re-baseline if project did not go to final ballot following the September 2018 posting.

## 2015-INT-01 (hidden)
Project | 2015-INT-01 | [5 empty] | Home
Project Name | Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec)
Status | Archived
Comments | Interpretation passed. FERC Approved, RD docket.
Deliverable | Interpretation CIP-002-5.1
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Low
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Al McMeekin
PMOS Liaison | Brian Murphy and Andrew Gallo
Affected Standards | CIP-002-5.1
Last Updated | 2017-02-09
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  | 2016-04-15 | 2016-04-29 | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-07-27 | 2016-09-12 | 2016-07-25 | 2016-09-08 | -2 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-10-13 | 2016-10-24 | 2016-10-04 | 2016-10-14 | -9 |  | 91.31% | 13
PTB - Present to BOT | 2016-11-15 | 2016-11-17 | 2016-11-15 | 2016-11-17 | 0 |  |  | 14
Filing - Filing with Regulators | 2016-11-28 | 2016-11-28 | 2016-12-28 | 2016-12-31 | 30 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Transfer RFI to the CIP SDT and update the SC | 2016-06-14 | Schedule updated to CIP SDT timeline.
Add CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison.
Archive Project | 2017-01-18 | Standard was filed on 11/28/2016 and may come off active monitoring by PMOS

## 2015-INT-02 (hidden)
Project | 2015-INT-02 | [5 empty] | Home
Project Name | Interpretation of CIP-007-5 for Foxguard Solutions
Status | Inactive
Comments | Currently on hold. SC approved RFI and for the interpretation drafting team to be formed in April 2016.
Deliverable | CIP-007-5
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Lacey Ourso
PMOS Liaison | Brian Murphy
Affected Standards | CIP-007-5
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  | 2016-05-15 | 2016-06-14 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2016-09-15 | 2016-10-30 | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archive | 2016-07-13 | PMOS agreed to archive. Project was eliminated.

## 2015-INT-03 (hidden)
Project | 2015-INT-03 | [5 empty] | Home
Project Name | Interpretation of TOP-002-2.1b for FMPP
Status | Inactive
Comments | Currently on hold. Interpretation drafting team recommendations were submitted to the SC in February 2016.
Deliverable | TOP-002-2.1b
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Low
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Lacey Ourso
PMOS Liaison | Brian Murphy
Affected Standards | TOP-002-2.1b
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2015-12-15 | 2016-01-05 | 2015-12-15 | 2016-01-05 | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2016-04-15 | 2016-05-30 | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  | 2016-08-10 | 2016-08-12 | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Last Status | 2016-02-01 | IDT nominees to be presented at February 2016 SC meeting.

## 2016-01 (hidden)
Project | 2016-01 | [5 empty] | Home
Project Name | Modifications to TOP and IRO Standards
Status | Archived
Comments | Preparing for final ballot in Dec 2016. NOPR issued June 18, 2015 (under previous project 2014-03). Final Rule issued November 19, 2015 with three directives with an associated 18 month regulatory filing deadline. The SC authorized posting at the June 2016 SC meeting. Standards passed additional ballot ending October 17 2016 and will be posted for final ballot early December 2016.
Deliverable | TOP/IRO Standards
Deadline | FERC deadline of July 27, 2017
Priority in RSDP, click to see applicable Footnote | High
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mark Olson
PMOS Liaison | Rod Kinard
Affected Standards | TOP/IRO Standards
Last Updated | 2016-12-13
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2016-01-22 | 2016-02-04 | 2016-04-18 | 2016-05-02 | 87 |  |  | 2
QR - Quality Review | 2016-05-10 | 2016-05-23 | 2016-06-27 | 2016-07-07 | 48 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-01-22 | 2016-02-22 | 2016-03-07 | 2016-04-06 | 45 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-06-20 | 2016-08-03 | 2016-07-11 | 2016-08-25 | 21 |  | IRO-002-5 (67.25%) TOP-001-4 (64.59%) | 8
CAB - Com/Add Ballot 2 | 2016-08-31 | 2016-10-17 | 2016-10-24 | 2016-12-08 | 54 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-12-02 | 2016-12-12 | 2017-01-17 | 2017-01-27 | 46 |  |  | 13
PTB - Present to BOT | 2017-02-07 | 2017-02-09 | 2017-02-07 | 2017-02-09 | 0 |  |  | 14
Filing - Filing with Regulators | 2017-03-09 | 2017-03-12 | 2017-03-09 | 2017-03-12 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Periodic Update | 2016-08-21 | Developer updated FERC deadline from 5/19/17 to 7/27/17
Archive Projectg | 2016-12-13 | Directed to archive at December 13, 2016 PMOS Meeting.

## 2016-02a (hidden)
Project | 2016-02 | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Archived
Comments | Petition was filed on March 3, 2017 requesting approval. TD at Lows resulted in a balloted CIP-003-7(i), which was not captured in the dates. "(i)" was dropped in the BOT presentation and filing and the standard was filed as CIP-003-7
Deliverable | LERC Definition & CIP-003-7
Deadline | Directive: March 31, 2017 (LERC only) (March 31 in SAR)
Priority in RSDP, click to see applicable Footnote | High
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Al McMeekin
PMOS Liaison | Ken Lanehome and Ash Mayfield
Affected Standards | CIP-003-7
Last Updated | 2017-04-11
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2016-03-10 | 2016-03-24 | 2016-03-10 | 2016-03-24 | 0 |  |  | 2
QR - Quality Review | 2016-06-30 | 2016-07-06 | 2016-06-30 | 2016-07-07 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-03-23 | 2016-04-21 | 2016-03-23 | 2016-04-21 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2016-06-01 | 2016-06-30 | 2016-06-01 | 2016-07-01 | 0 | Expanded Scope |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2016-07-21 | 2016-09-06 | 2016-07-25 | 2016-09-08 | 4 |  |  | 8
CAB - Com/Add Ballot 2 | 2016-10-21 | 2016-12-05 | 2016-10-17 | 2016-12-01 | -4 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2016-12-09 | 2016-12-19 | 2017-01-05 | 2017-01-15 | 27 |  | 87.95% | 13
PTB - Present to BOT | 2017-02-08 | 2017-02-10 | 2017-02-08 | 2017-02-10 | 0 |  |  | 14
Filing - Filing with Regulators | 2017-03-03 | 2017-03-06 | 2017-03-28 | 2017-03-31 | 25 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archived comments | 2016-06-10 | Order 822 was issued on January 21, 2016. The SC authorized posting the SAR and to request nominations for additional team members at March 9, 2016 meeting. The SAR posting ended April 21, 2016 and the SDT is reviewing the comments received. A CIP Technical Conference was held on April 19, 2016 in Atlanta. Seven additional members were appointed to the SDT at the April 20, 2016 SC meeting. Initial SDT meeting May 24-26, 2016 in Atlanta.
Added CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison. Second SAR posting was required due to expansion of scope.
Liaison Change | 2017-03-15 | Updated B. Murpy and A. Gallow to K. Lanehome and A. Mayfield
Archived | 2017-04-01 | Project was filed with regulators.

## 2016-02b (hidden)
Project | 2016-02 | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Archived
Comments | CIP-012-1 was approved by industry and the NERC Board adopted the standard at its August 2018 meeting and filed with regulatory authorities on September 18, 2018.
Deliverable | Directives, Control Center Comm Nets (CIP-012-1)/ Control Center definition
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | 2
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome, Ash Mayfield, and Kirk Rosener
Affected Standards | CIP-012-1
Last Updated | 2018-09-24
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-10-20 | 2016-10-30 | 2016-10-20 | 2016-10-30 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-02-10 | 2017-03-13 | [5 empty] | 6
CP2 - Comment Period 2 | 2017-08-14 | 2017-09-12 | 2016-12-02 | 2017-01-16 | -255 |  | Informal for definition | 7
CIB - Com/Ballot 1 (Initial) | 2017-07-27 | 2017-09-11 | 2017-03-31 | 2017-05-15 | -118 |  |  | 8
CAB - Com/Add Ballot 2 | 2017-10-27 | 2017-12-11 | 2017-08-15 | 2017-09-29 | -73 |  | Does not include the informal 21 day comment on Implementation Guidance ending on 12/11/2017 | 9
CAB - Com/Add Ballot 3 | 2018-03-16 | 2018-04-30 | [5 empty] | 10
CAB - Com/Add Ballot 4 | 2018-05-18 | 2018-07-02 | [5 empty] | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-08-02 | 2018-08-09 | 2017-10-17 | 2017-10-27 | -289 |  |  | 13
PTB - Present to BOT | 2018-11-06 | 2018-11-08 | 2017-11-07 | 2017-11-09 | -364 |  |  | 14
Filing - Filing with Regulators | 2018-12-01 | 2018-12-04 | 2017-12-28 | 2017-12-31 | -338 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archived comments | 2016-06-10 | Order 822 was issued on January 21, 2016. The SC authorized posting the SAR and to request nominations for additional team members at March 9, 2016 meeting. The SAR posting ended April 21, 2016 and the SDT is reviewing the comments received. A CIP Technical Conference was held on April 19, 2016 in Atlanta. Seven additional members were appointed to the SDT at the April 20, 2016 SC meeting. Initial SDT meeting May 24-26, 2016 in Atlanta.
Added CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison.
Liaison Change | 2017-03-15 | Updated B. Murpy and A. Gallow to K. Lanehome and A. Mayfield
Developer Change | 2017-04-01 | Replaced Al McMeekin with Mat Bunch and Katherine Street.
Change in Approach | 2017-06-27 | Team decided to create CIP-012-1 and not modiifying CIP-006 for Communcation Networks.
Developer Change | 2018-02-14 | Replaced Katherine Street with Jordan Mallory
Developer Change | 2018-06-13 | Mat Bunch was removed from the project.
Archive Project | 2018-10-18 | Project archived per instructions at the September 13, 2018 PMOS meeting.
Formulas:
Projected or Actual End = [Projected or Actual Start]+10
Projected or Actual End = +[Projected or Actual Start]+3
Baseline End = [Baseline Start]+10
Baseline End = +[Baseline Start]+3

## 2016-02c
Project | 2016-02 | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Responding to Comment
Comments | The SDT will be meeting with the 2015-9 SOL SDT on November 6-8 to align the CIP-002 standard with the SOL work.
Deliverable | Address TO Control Centers Performing Transmission Operator (TOP) Obligations.
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome, Ash Mayfield, and Kirk Rosener
Affected Standards | CIP-002-5.1a
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-10-20 | 2016-10-30 | 2016-10-20 | 2016-10-30 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-03-14 | 2017-04-11 |  |  |  |  | Added to schedule, reduced period - SDT needed feedback | 6
CP2 - Comment Period 2 | 2018-06-14 | 2018-07-13 |  |  |  |  | IROL for CIP-002 | 7
CIB - Com/Ballot 1 (Initial) | 2017-09-14 | 2017-10-30 | 2016-12-02 | 2017-01-15 | -286 |  | See notes for 8/10 and 8/25. | 8
CAB - Com/Add Ballot 2 | 2017-12-05 | 2018-01-18 | 2017-03-31 | 2017-05-14 | -249 |  |  | 9
CAB - Com/Add Ballot 3 | 2018-08-23 | 2018-10-09 | 2017-08-15 | 2017-09-28 | -373 |  | Going back to initial ballot | 10
CAB - Com/Add Ballot 4 | [7 empty] | 11
CAB - Com/Add Ballot 5 | [7 empty] | 12
FB - Final Ballot | 2019-01-25 | 2018-02-15 | 2017-10-17 | 2017-10-27 | -465 |  |  | 13
PTB - Present to BOT | 2019-02-06 | 2019-02-08 | 2017-11-07 | 2017-11-09 | -456 |  |  | 14
Filing - Filing with Regulators | 2019-04-01 | 2019-04-04 | 2017-12-28 | 2017-12-31 | -459 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Archived comments | 2016-06-10 | Order 822 was issued on January 21, 2016. The SC authorized posting the SAR and to request nominations for additional team members at March 9, 2016 meeting. The SAR posting ended April 21, 2016 and the SDT is reviewing the comments received. A CIP Technical Conference was held on April 19, 2016 in Atlanta. Seven additional members were appointed to the SDT at the April 20, 2016 SC meeting. Initial SDT meeting May 24-26, 2016 in Atlanta.
Added CIP Schedule for approval | 2016-07-20 | Update SC that schedule was approved by SDT, SDT leadership, developer, and PMOS Liaison.
Liaison Change | 2017-03-15 | Updated B. Murpy and A. Gallow to K. Lanehome and A. Mayfield
Developer Change | 2017-04-01 | Replaced Al McMeekin with Mat Bunch and Katherine Street.
Schedule Adjustment | 2017-08-10 | The original 5/15/2017 planned posting was accepted for 9/18 to stagger 2013-03, 2015-09, and 2015-10.
Schedule Adjustment | 2017-08-25 | The posting was advanced due to 2015-09 (SOL) being moved from its 9/12 posting to 9/30.
Developer Change | 2018-02-14 | Replaced Katherine Street with Jordan Mallory
SC Action | 2018-06-13 | The SC accepted the SAR to address recommended revisions to CIP-002 provided by Project 2015-09 Establish and Communicate System Operating Limits (FAC SOL) SDT; authorize the Project 2016-02 SDT to revise the CIP Reliability Standards based on the modifications provided by the FAC SOL SDT; and authorize posting of the SAR for a 30-day informal comment period.
Developer Change | 2018-06-13 | Mat Bunch was removed from the project.
Formulas:
Projected or Actual End = [Projected or Actual Start]+10
Projected or Actual End = +[Projected or Actual Start]+3
Baseline End = [Baseline Start]+10
Baseline End = +[Baseline Start]+3

## 2016-EPR-01 (hidden)
Project | 2016-EPR-01 | [5 empty] | Home
Project Name | Enhanced Periodic Review of Personnel Performance, Training, and Qualifications Standards
Status | Archived
Comments | The team will be requesting the Standards Committee at the June 14, 2017 meeting to accept a SAR to revise a Standard and to activate Project 2017-02.
Deliverable | PER-003-1 and PER-004-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Mike Brytowski
Affected Standards | PER-003-1 and PER-004-2, but PER-001-0.2 was not evaluated due to retirement on April 17, 2017.
Last Updated | 2017-06-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-02-10 | 2016-02-23 | 2016-02-10 | 2016-02-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-01-10 | 2017-02-23 | 2017-01-23 | 2017-03-08 | 13 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
PMOS request | 2017-12-13 | List only the EPR nomination period and recommendation posting dates.
Archive Project | 2017-06-14 | Project 2017-02 initiated to address the EPR recommendation(s).

## 2016-EPR-02 (hidden)
Project | 2016-EPR-02 | [5 empty] | Home
Project Name | Enhanced Periodic Review of Voltage and Reactive Standards
Status | Archived
Comments | The periodic review team (PRT) responded to industry comments that affirm the PRT's recommendations. The PRT maintained its initial recommendation that the standards are sufficient to protect reliablity and although some things could be cleaned up, the recommendation is to not open the standards for revisions (i.e., yellow rating). The PRT will present their recommendations for acceptance to the Standards Committee on June 14, 2017 and to re-affirm the two VAR standards.
Deliverable | VAR-001-4.1 & VAR-002-4
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Scott Barfield-McGinnis
PMOS Liaison | Amy Casuscelli
Affected Standards | VAR-001-4.1 & VAR-002-4
Last Updated | 2017-06-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-02-10 | 2016-02-23 | 2016-02-10 | 2016-02-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-02-28 | 2017-04-13 | 2017-01-31 | 2017-03-17 | -28 | Other |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
PMOS request | 2017-12-13 | List only the EPR nomination period and recommendation posting dates.
Delay - Other | 2017-02-08 | Team cleaned up templates via conference calls after in-person meeting adding two weeks, plus the Standards Committee's Standing Review Team asked for a minimum of two weeks to review.
Archive Project | 2017-06-14 | Recommendations accepted by the SC and the standards were re-affirmed.

## 2016-02d
Project | 2016-02 | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Posted
Comments | The SDT will be posting for a 45-day informal comment period on November 2 through December 18, 2018.
Deliverable | Address all remaining V5TAG issues: Cyber Asset and BES CA (BCA) definitions, Network and Externally Accessible Devices (ESP, ERC, IRA), Obligations, Virtualization, and CIP Exceptional Circumstances.
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome, Ash Mayfield, and Kirk Rosener
Affected Standards | CIP-005, CIP-007 and CIP-010
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review | 2016-10-20 | 2016-10-30 | 2016-10-20 | 2016-10-30 | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2018-11-02 | 2018-12-18 |  |  |  |  | 3rd Informal posting | 5
CP1 - Comment Period 1 | 2017-03-14 | 2017-04-11 | 2017-03-14 | 2017-04-11 | 0 |  |  | 6
CP2 - Comment Period 2 | 2017-10-06 | 2017-11-02 |  |  |  |  | Unplanned | 7
CIB - Com/Ballot 1 (Initial) | 2018-09-13 | 2018-10-27 | 2018-09-13 | 2018-10-29 |  |  |  | 8
CAB - Com/Add Ballot 2 | 2018-12-14 | 2019-01-28 | 2018-12-14 | 2019-01-28 | 0 |  |  | 9
CAB - Com/Add Ballot 3 | 2019-03-05 | 2019-04-19 | 2019-03-02 | 2019-04-19 | -3 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-05-13 | 2019-05-23 | 2019-05-13 | 2019-05-23 |  |  |  | 13
PTB - Present to BOT | 2019-08-06 | 2019-08-08 | [5 empty] | 14
Filing - Filing with Regulators | 2019-09-01 | 2019-09-04 | [5 empty] | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Segmented project | 2017-08-08 | This fourth segment of the project was made to address all remaining V5TAG issues: Cyber Asset and BES CA (BCA) definitions, Network and Externally Accessible Devices (ESP, ERC, IRA), Obligations, Virtualization, and CIP Exceptional Circumstances.
Assign PMOS Liaison | 2017-10-12 | Assigned Kirk Rosener to support Ken Lanehome and Ash Mayfield.
Developer Change | 2018-02-14 | Replaced Katherine Street with Jordan Mallory
Developer Change | 2018-06-13 | Mat Bunch was removed from the project.
Accept baseline schedule | 2018-09-13 | PMOS accepted the baseline following appointment of additional members in July 2018.
Delay | 2018-09-01 | Project delayed from August 2018 to January 2019 (tentatively) for 2018-02, CIP-008 to finish.
Formulas:
Projected or Actual End = [Projected or Actual Start]+10
Projected or Actual End = +[Projected or Actual Start]+44
Baseline End = [Baseline Start]+10

## 2016-03 (hidden)
Project | 2016-03 | [5 empty] | Home
Project Name | Cyber Security Supply Chain Management
Status | Archived
Comments | The petition was filed on September 26, 2017.
Deliverable | New and revised Standard(s)
Deadline | 2017-09-27
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | 1
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mark Olson
PMOS Liaison | Brenda Hampton
Affected Standards | CIP-005-6, CIP-010-3, and CIP-013-1
Last Updated | 2017-10-03
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2016-07-29 | 2016-08-18 | 2016-07-29 | 2016-08-18 | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-10-20 | 2016-11-18 | 2016-10-20 | 2016-11-21 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-01-19 | 2017-03-06 | 2017-01-19 | 2017-03-06 | 0 |  |  | 8
CAB - Com/Add Ballot 2 | 2017-05-02 | 2017-06-15 | 2017-04-12 | 2017-05-26 | -20 |  | CIP-005-6 89.84% CIP-010-3 82.92% CIP-013-1 88.64% | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2017-07-11 | 2017-07-20 | 2017-06-21 | 2017-06-30 | -20 |  | CIP-005-6 88.79% CIP-010-3 81.40% CIP-013-1 884.19% | 13
PTB - Present to BOT | 2017-08-09 | 2017-08-11 | 2017-08-09 | 2017-08-11 | 0 |  |  | 14
Filing - Filing with Regulators | 2017-09-26 | 2017-09-26 | 2017-09-24 | 2017-09-27 | -2 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Create project record | 2016-08-01 | Added project to PTS.
Periodic Update | 2016-08-21 | Added FERC deadline.
Baseline Schedule | 2016-11-30 | SDT determined the schedule.
Present Schedule to SC | 2017-03-15 | Accepted the SDT project schedule.
Removed Liaison | 2017-04-14 | Removed R. Kinard due to resigning from PMOS.
Removed Liaison | 2017-07-27 | A. Kimmey due to leaving company.
Archive Project | 2017-10-12 | PMOS Archived the project as it was file on 9/26/2017.
Formulas:
Baseline End = +[Baseline Start]+32
Projected or Actual End = +[Projected or Actual Start]+2
Note on E33: FERC Deadline

## 2016-04 (hidden)
Project | 2016-04 | [5 empty] | Home
Project Name | Modifications to PRC-025-1
Status | Archived
Comments | Providing the SC an update on a non-substantive correction (Vlowside to Vhighside) to the Guidelines and Technical Basis before filing.
Deliverable | PRC-025-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | Yes
Developer | Scott Barfield-McGinnis
PMOS Liaison | Charles Yeung
Affected Standards | PRC-025-1
Last Updated | 2018-03-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2016-09-16 | 2016-09-28 | 2016-09-16 | 2016-09-28 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2016-09-16 | 2016-10-18 | 2016-09-16 | 2016-10-18 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2017-03-20 | 2017-04-03 | 2017-03-02 | 2017-04-01 | -18 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2017-07-25 | 2017-09-07 | 2017-07-26 | 2017-09-08 | 1 |  |  | 8
CAB - Com/Add Ballot 2 | 2017-10-30 | 2017-12-14 | 2017-10-24 | 2017-12-07 | -6 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-01-09 | 2018-01-18 | 2018-01-09 | 2018-01-18 | 0 |  |  | 13
PTB - Present to BOT | 2018-02-07 | 2018-02-09 | 2018-02-07 | 2018-02-09 | 0 |  |  | 14
Filing - Filing with Regulators | 2018-03-07 | 2018-03-10 | 2018-03-07 | 2018-03-10 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
SC Authorized Posting | 2016-09-14 | SAR and SAR SDT nominations.
Accept Baseline Schedule | 2017-07-27 | Accepted by PMOS.
Archive Project | 2018-03-14 | PMOS Archived the project following the filing.
Formulas:
Baseline End = +[Baseline Start]+30
Projected or Actual End = +[Projected or Actual Start]+44

## 2016-02e
Project | 2016-02 | [5 empty] | Home
Project Name | Modifications to CIP Standards
Status | Responding to Comment
Comments | The CIP-003 standard was posted for comment and initial ballot through October 9, 2018. The ballot passed at 90.06%. The drafting team will meet through November and December to respond to comments and to determine next steps.
Deliverable | CIP-003-8 (FERC Order No. 843 Malicious Code Example Directive)
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, High
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Jordan Mallory
PMOS Liaison | Ken Lanehome, Ash Mayfield, and Kirk Rosener
Affected Standards | CIP-003-7
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-08-23 | 2018-10-09 | 2018-08-23 | 2018-10-07 | 0 |  |  | 8
CAB - Com/Add Ballot 2 | 2018-11-22 | 2019-01-06 | 2018-11-22 | 2019-01-06 | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-01-25 | 2019-02-04 | 2019-01-25 | 2019-02-04 | 0 |  |  | 13
PTB - Present to BOT | 2019-02-06 | 2019-02-08 | 2019-02-06 | 2019-02-08 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-03-06 | 2019-03-08 | 2019-03-06 | 2019-03-08 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Segmented project | 2018-07-30 | CIP-003 for malicous code was segmented into its own tracking worksheet.
Accept Baseline | 2018-10-31 | PMOS accepted the baseline provided by the SDT.
Formulas:
Baseline End = +[Baseline Start]+45
Projected or Actual End = +[Projected or Actual Start]+45

## 2017-01
Project | 2017-01 | [5 empty] | Home
Project Name | Modifications to BAL-003-1.1
Status | Pending SC Action
Comments | The SDT held a conference call on October 19 to finalize documentation for authorization of a formal posting for comment and initial ballot to the SC at its November meeting.
Deliverable | BAL-003-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Amy Casuscelli & Linda Lynch
Affected Standards | BAL-003-1.1
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-06-19 | 2017-07-03 | 2017-06-19 | 2017-07-03 | 0 |  |  | 1
Nominations - DT | 2017-07-27 | 2017-08-09 | 2017-07-27 | 2017-08-09 | 0 |  | Supplemental Nominations | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-06-19 | 2017-07-18 | 2017-06-19 | 2017-07-18 | 0 |  | By NERC RS | 4
SP2 - SAR/PR/WP Posting 2 | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2017-12-01 | 0 |  | By NWPP FRSG | 5
CP1 - Comment Period 1 | 2018-09-06 | 2018-09-20 |  |  |  |  | Unscheduled posting | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-11-26 | 2019-01-09 | 2018-11-06 | 2019-01-09 | -20 |  |  | 8
CAB - Com/Add Ballot 2 | 2019-02-18 | 2019-04-03 | 2019-02-18 | 2019-04-03 | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-04-16 | 2019-04-25 | 2019-04-16 | 2019-04-25 | 0 |  |  | 13
PTB - Present to BOT | 2019-05-09 | 2019-05-11 | 2019-05-09 | 2019-05-11 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-06-09 | 2019-06-16 | 2019-06-09 | 2019-06-16 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Amy Casuscelli accepted appointment as PMOS liaison.
Assign PMOS Liaison | 2017-10-12 | Add Linda Lynch to support Amy Casuscelli.
Updated Standard Number | 2018-06-06 | Changed standard from BAL-003-1 to BAL-003-1.1.
Accept baseline | 2018-07-18 | PMOS accepted baseline project schedule.

## 2017-02 (hidden)
Project | 2017-02 | [5 empty] | Home
Project Name | Modifications to Personnel Performance, Training, and Qualifications Standards
Status | Archived
Comments | NERC filed a petition for approval of PER-003 on July 23, 2018. Project archived by PMOS on Spetmber 13, 2018.
Deliverable | PER-003-2, retire PER-004-2
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Mike Brytowski
Affected Standards | PER-003-1 & PER-004-2
Last Updated | 2018-09-13
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  | EPR SDT appointed as SDT | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-06-21 | 2017-07-24 | 2017-06-21 | 2017-07-24 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-01-22 | 2018-03-07 | 2018-01-22 | 2018-03-07 | 0 |  | 97.5% | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-04-03 | 2018-04-12 | 2018-04-27 | 2018-05-06 | 24 |  |  | 13
PTB - Present to BOT | 2018-05-09 | 2018-05-11 | 2018-05-09 | 2018-05-11 | 0 |  |  | 14
Filing - Filing with Regulators | 2018-07-23 | 2018-07-23 | 2018-06-09 | 2018-06-11 | -44 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Mike Brytowski accepted appointment as PMOS liaison.
Accept Baseline | 2018-01-31 | PMOS accepted baseline.
Archive Project | 2018-09-13 | PMOS archived project as it was filed on July 23, 2018
Formulas:
Baseline End = +[Baseline Start]+9
Projected or Actual End = +[Projected or Actual Start]+2

## 2017-03
Project | 2017-03 | [5 empty] | Home
Project Name | Periodic Review of FAC-008-3 Standard
Status | On Hold
Comments | The periodic review team delivered their review recommendation to the SC in March 2018. The recommendation is to reaffirm with an action to revise, but at a later time. No action will be taken or archiving of the PTS item until the Standards Efficiency Reviews are complete.
Deliverable | PR Recommendations
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low (was Medium previously)
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Al McMeekin
PMOS Liaison | Mark Pratt
Affected Standards | FAC-008-3
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-05-10 | 2017-05-23 | 2017-05-10 | 2017-05-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-10-30 | 2017-12-13 | 2017-10-30 | 2017-12-13 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Mark Pratt accepted appointment as PMOS liaison.

## 2017-04
Project | 2017-04 | [5 empty] | Home
Project Name | Periodic Review of Interchange Scheduling and Coordination Standards
Status | On Hold
Comments | The response to comments are complete. Comments were in favor of the recommendations being made by the team which is to retire one standard and drop terms which are unclear in the standards. Periodic Review of subset INT Standards will provide the Standards Efficiency Review Team (SER) (Gary Nolan is the contact person) with the initial recommendations of the INT periodic review team, as well as all associated documents this week. No future meetings or postings expected for now. Project 2017-04 will then be placed on hold pending Standards Efficiency Review team recommendations/findings. No recommendations have been made to the Standards Committee.
Deliverable | PR Recommendations
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low (was Medium previously)
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Charles Yeung
Affected Standards | INT-004, INT-006, INT-009, and INT-010
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-05-02 | 2017-05-15 | 2017-05-02 | 2017-05-15 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2018-01-10 | 2018-02-23 | [5 empty] | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Charles Yeung accepted appointment as PMOS liaison.

## 2017-05
Project | 2017-05 | [5 empty] | Home
Project Name | Periodic Review NUC-001-3
Status | On Hold
Comments | The review template 45-day posting for preliminary recommendations ended January 29, 2018. There is a meeting scheduled for March 19 to review industry comments and discuss the team’s final recommendation. Given the overwhelming industry support for the team’s Preliminary Recommendation (Yellow-Revise), they do not anticipate a change in the recommended “color” of the standard. The PRT recommends to reaffirm the standard and has placed the project on hold pending the Standards Efficiency Reivew outcomes.
Deliverable | PR Recommendations
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low (was Medium previously)
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mat Bunch
PMOS Liaison | Amy Casuscelli and Colby Bellville
Affected Standards | NUC-001-3
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-05-10 | 2017-05-23 | 2017-05-10 | 2017-05-23 | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2017-12-15 | 2018-01-29 | 2017-12-04 | 2018-01-17 | -11 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-10 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Amy Casuscelli accepted appointment as PMOS liaison.
Assign PMOS Liaison | 2017-10-12 | Assigned Colby Bellville to support Amy Casuscelli (new SC vice chair)
Formulas:
Baseline End = +[Baseline Start]+44

## 2017-06 (hidden)
Project | 2017-06 | [5 empty] | Home
Project Name | Project 2017-06 Modifications to BAL-002-2
Status | Archived
Comments | NERC filed a petition for approval on August 17, 2018. The project was archived by the PMOS on September 13, 2018.
Deliverable | BAL-002-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 8, Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Darrel Richardson
PMOS Liaison | Ken Lanehome
Affected Standards | BAL-002-2
Last Updated | 2018-09-13
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-06-20 | 2017-07-03 | 2017-06-20 | 2017-07-03 | 0 |  |  | 1
Nominations - DT | 2017-07-27 | 2017-08-09 | 2017-07-27 | 2017-08-09 | 0 |  | Supplemental Nominations | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-06-20 | 2017-07-20 | 2017-06-20 | 2017-07-20 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-03-22 | 2018-05-08 | [5 empty] | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2018-06-29 | 2018-07-08 | [5 empty] | 13
PTB - Present to BOT | 2018-08-15 | 2017-08-17 | [5 empty] | 14
Filing - Filing with Regulators | 2018-08-17 | 2018-08-20 | [5 empty] | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Created Project in PTS | 2017-05-30 | Created Project record.
Assign PMOS Liaison | 2017-06-14 | Ken Lanehome accepted appointment as PMOS liaison.
SAR | 2018-02-14 | SC accepts the final SAR.
Accept Baseline | N/A | Project schedule baseline was never submitted to PMOS.
Archive Project | 2018-09-13 | PMOS archived project as it was filed on August 17, 2018.
Formulas:
Projected or Actual End = +[Projected or Actual Start]+9

## 2017-07
Project | 2017-07 | [5 empty] | Home
Project Name | Stds Alignment with Registration
Status | On Hold
Comments | The project is on a temporary hold for coordination with other projects (such as Standards Efficiency Review and CIP) because many of the requirements that address these functional entities, are being considered for retirement. The project is not as simple as just removing a requirement with PSE, IA or LSE. The removal of the requirement may create a gap that would need to be addressed by another functional entity such as Distribution Provider (DP) or Transmission Owner (TO). This project is not addressing a reliability issue and has a low priority in the RSDP; therefore, the project is in a holding pattern in the interim.
Deliverable | Standards with PSE, IA, or LSE
Deadline
Priority in RSDP, click to see applicable Footnote | Footnote 9, Low
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Mike Brytowski
Affected Standards | Standards with PSE, IA, or LSE
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2017-08-01 | 2017-08-14 | 2017-08-01 | 2017-08-14 | 0 |  |  | 1
Nominations - DT | 2018-05-01 | 2018-05-14 | [5 empty] | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2017-08-01 | 2017-08-30 | 2017-08-01 | 2017-08-30 | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2017-12-11 | 2018-01-09 | 2017-12-07 | 2018-01-06 | -4 |  |  | 5
CP1 - Comment Period 1 | 2018-02-01 | 2018-03-02 | 2018-02-01 | 2018-03-02 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  | 2018-09-17 | 2018-11-01 | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  | 2018-12-04 | 2018-12-14 | 0 |  |  | 13
PTB - Present to BOT |  |  | 2019-02-05 | 2019-02-08 | 0 |  |  | 14
Filing - Filing with Regulators |  |  | 2019-03-07 | 2019-03-10 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Assign PMOS Liaison | 2017-07-27 | Mike Brytowski accepted appointment as PMOS liaison.
SC Action | 2018-06-13 | SC appoint drafting team as recommended by NERC staff.
Accept Baseline | 2018-09-13 | PMOS accepted based line as presented to the members.
Schedule adjustment | 2018-10-31 | The PMOS removed the "projected schedule" as it was inaccurate and misleading.
Formulas:
Baseline End = +[Baseline Start]+13
Baseline Start = +[Baseline Start, row above]+30

## 2018-01
Project | 2018-01 | [5 empty] | Home
Project Name | Canadian-specific Revisions to TPL-007-2
Status | Posted
Comments | The team met in September to respond to stakeholder comments. The standard is posted for a 45-day initial comment period and initial ballot through November 15, 2018.
Deliverable | TPL-007-3
Deadline | N/A
Priority in RSDP, click to see applicable Footnote | Footnote 10, Medium
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Mat Bunch
PMOS Liaison | Charles Yeung
Affected Standards | TPL-007-2
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2018-03-30 | 2018-04-19 | [5 empty] | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-03-30 | 2018-04-30 | 2018-03-30 | 2018-04-30 |  |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 | 2018-08-10 | 2018-09-06 | 2018-08-10 | 2018-09-09 | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-10-02 | 2018-11-15 | 2018-10-05 | 2018-11-19 | 3 |  |  | 8
CAB - Com/Add Ballot 2 | 2018-12-06 | 2019-01-20 | 2018-12-06 | 2019-01-20 | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-01-24 | 2019-02-03 | 2019-01-24 | 2019-02-03 | 0 |  |  | 13
PTB - Present to BOT | 2019-02-07 | 2019-02-09 | 2019-02-07 | 2019-02-09 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-03-07 | 2019-03-09 | 2019-03-07 | 2019-03-09 | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Assign PMOS Liaison | 2018-04-25 | C. Yeung acccept to follow project.
Accept baseline schedule | 2018-09-13 | PMOS accepted the baseline schedule as presented to the members.
Corrected BOT Date | 2018-10-03 | Baseline incorrectly listed BOT delivery for May 2019 and it should have been Feb 2019.
Formulas:
Baseline End = +[Baseline Start]+30
Projected or Actual End = +[Projected or Actual Start]+45

## 2018-02
Project | 2018-02 | [5 empty] | Home
Project Name | Modifications to CIP-008 Cyber Security Incident Reporting
Status | Posted
Comments | The abbreviated comment period and initial ballot ended on October 22, 2018. The ballot failed considerably at 20.02%. NOTE: The second posting is scheduled for November 14, 2018. The comment period and ballot period considerably shorter to be able to work toward the January 2019 deadline.
Deliverable | CIP-008-6
Deadline | 2019-01-19
Priority in RSDP, click to see applicable Footnote | Footnote 10, High
P81 Req (2013) | N/A
Number of Directives | Order No. 848 (1 Directive, 4 elements)
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Alison Oswald
PMOS Liaison | Colby Bellville & Amy Casuscelli
Affected Standards | CIP-008-5
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2018-08-10 | 2018-08-29 | 2018-08-10 | 2018-08-30 |  |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-08-10 | 2018-09-10 | 2018-08-10 | 2018-09-09 |  |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2018-10-03 | 2018-10-22 | 2018-10-04 | 2018-10-24 | 1 |  |  | 8
CAB - Com/Add Ballot 2 | 2018-11-14 | 2018-11-29 | 2018-11-14 | 2018-11-29 | 0 |  |  | 9
CAB - Com/Add Ballot 3 | 2018-12-08 | 2018-12-23 | [5 empty] | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot | 2019-01-14 | 2019-01-19 | 2019-01-14 | 2019-01-19 | 0 |  |  | 13
PTB - Present to BOT | 2019-02-06 | 2019-02-08 | 2019-02-06 | 2019-02-08 | 0 |  |  | 14
Filing - Filing with Regulators | 2019-02-09 | 2019-02-10 | [5 empty] | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
SC Action | 2018-08-09 | SCEC authorized posting of the SAR and solicitation of nominations.
Project added to PTS | 2018-08-10 | Added project for tracking by PMOS.
Assign PMOS Liaison | 2018-09-13 | PMOS appointed Colby Belleville and Amy Casuscelli to the project.
SC Action | 2018-10-02 | SCEC authorized posting with shortened (waiver) posting periods.
Accept Baseline | 2018-10-31 | PMOS accepted the baseline schedule (periods are compressed as approved by SC).
Formulas:
Baseline End = +[Baseline Start]+20
Projected or Actual End = +[Projected or Actual Start]+15

## 2017-08 (hidden)
Project | 2017-08 | [5 empty] | Home
Project Name | Open - Available
Status | Inactive
Comments
Deliverable | CIP-014-4
Deadline
Priority in RSDP, click to see applicable Footnote
P81 Req (2013)
Number of Directives
No. of Guidances (see Note 2)
Directionally consistent with IERP findings (See Note 5)
Developer | Mat Bunch
PMOS Liaison
Affected Standards
Last Updated | 2017-07-17
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Assign PMOS Liaison | 2017-07-27

## 2018-03
Project | 2018-03 | [5 empty] | Home
Project Name | Standards Efficiency Review - Phase I
Status | Nominations
Comments
Deliverable | Retirements Only
Deadline
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | Laura Anderson
PMOS Liaison | Mark Pratt & Michael Brytowski
Affected Standards | Various
Last Updated | 2018-11-14
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT | 2018-08-28 | 2018-09-17 | [5 empty] | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2018-08-28 | 2018-09-26 | [5 empty] | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
New Project | 2018-08-22 | SC authorized project.

## 2018-04 (hidden)
Project | 2018-04 | [5 empty] | Home
Project Name | PRC-024-2 and Inverter Based Resources
Status | Inactive
Comments | The two SARs were presented to the SC on September 13, 2018. Both SARs were rejected by the SC due to other industry work that is underway. A rejection letter was sent to CAISO by the SC Chair on September 21, 2018.
Deliverable | TBD
Deadline
Priority in RSDP, click to see applicable Footnote | N/A
P81 Req (2013) | N/A
Number of Directives | N/A
No. of Guidances (see Note 2) | N/A
Directionally consistent with IERP findings (See Note 5) | N/A
Developer | TBD
PMOS Liaison | TBD
Affected Standards | PRC-024-2
Last Updated | 2018-09-24
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR |  |  |  |  | 0 |  |  | 1
Nominations - DT |  |  |  |  | 0 |  |  | 2
QR - Quality Review |  |  |  |  | 0 |  |  | 3
SP1 - SAR/PR/WP Posting 1 |  |  |  |  | 0 |  |  | 4
SP2 - SAR/PR/WP Posting 2 |  |  |  |  | 0 |  |  | 5
CP1 - Comment Period 1 |  |  |  |  | 0 |  |  | 6
CP2 - Comment Period 2 |  |  |  |  | 0 |  |  | 7
CIB - Com/Ballot 1 (Initial) |  |  |  |  | 0 |  |  | 8
CAB - Com/Add Ballot 2 |  |  |  |  | 0 |  |  | 9
CAB - Com/Add Ballot 3 |  |  |  |  | 0 |  |  | 10
CAB - Com/Add Ballot 4 |  |  |  |  | 0 |  |  | 11
CAB - Com/Add Ballot 5 |  |  |  |  | 0 |  |  | 12
FB - Final Ballot |  |  |  |  | 0 |  |  | 13
PTB - Present to BOT |  |  |  |  | 0 |  |  | 14
Filing - Filing with Regulators |  |  |  |  | 0 |  |  | 15
PT - Post Approval Training |  |  |  |  | 0 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
New Project | 2018-09-13 | Project is indefinitely on hold due to SC rejecting the SARs.

## Footnotes
| FOOTNOTES | Home
No. | Description | Back to:
Note 1 | 2015-2017 RSDP The prioritizations here reflect those prioritizations assigned as part of the 2015-2017 Reliability Standards Development Plan (RSDP). In its approach to prioritizing Reliability Standards projects, the RSDP considered how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill-in-the-blank status and five-year assessment commitments). Some projects were not prioritized in the RSDP, as they were originally anticipated to be complete before the end of the first quarter of 2015, and those projects have an "N/A" designation in this column. Other projects have been added to the Project Tracking Spreadsheet that were not prioritized in the RSDP. These were added in response to regulatory directives that were issued following completion of the RSDP, and they will be prioritized according to the same process during the first quarter of 2015 according to the same process described in the RSDP. Those projects are designated as "Pending Prioritization in 1Q 2015." As discussed in the 2015-2017 RSDP, the prioritization will occur in collaboration between NERC Staff and the Standards Committee. | 2015-09
Note 2 | Refers to guidances from regulatory orders for standards activity to consider, but that do not carry the same effect as a directive. | 2015-09b
Note 3 | In the columns at right, in some cases, an "additional ballot" is not indicated for planning purposes, but if consensus is not supported on an initial ballot, or if substantive changes occur, one will be scheduled. | 2015-10
Note 4 | In the columns at right, there are no "plan" milestones in some cases because the project was originally planned to be complete in 2014, and the project's "actual" milestones have extended into 2015). | 2016-02b
Note 5 | In the column labeled "directionally consistent with IERP findings," directionally consistent indicates whether the Standard Drafting Team, when the project is completed, considered the recommendations from the Independent Expert Review Project and the Paragraph 81 project. After the Standard Drafting Team has considered the recommendations, the materials posted with the standards will describe the Standard Drafting Team's consideration of the findings. | 2016-02c
Note 6 | Baseline - SC Approved project schedule. Current - Standards Developer managed schedule. Proposed - Not approved, used for planning purposes. Archived-Current - Project completed or abandoned. Archived-Baseline - Project completed or abandoned. Open-Baseline - Reserved for future project. Open-Current - Reserved for future project. N/A - Scheduling is not applicable. | 2016-02d
Note 7 | 2016-2018 RSDP The following projects are planned to continue from 2015 along with any 2015 projects that are planned to be completed in that year but need additional time. As in the 2015–2017 RSDP, the approach to prioritizing Reliability Standards projects in this RSDP addressed how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill‐in‐the‐blank status and five‐year assessment commitments). The prioritization gave primary consideration to RISC category rankings, regulatory directives, and regulatory deadlines. Based on the application of these elements, this section prioritizes each Reliability Standard project as high, medium, low, or pending technical committee input. | 2016-02e
Note 8 | 2017-2019 RSDP The approach to prioritizing Reliability Standards projects in this RSDP is consistent with previous RSDPs. Specific elements include: (1) RISC Category Rankings; (2) regulatory directives and deadlines; (3) Reliability Standard requirements recommended for retirement; (4) the IERP content and quality assessments; and (5) additional considerations (fill-in-the-blank status and five-year assessment commitments). The prioritization considers RISC category rankings, regulatory directives, and regulatory deadlines. Based on the application of these elements, this section prioritizes each Reliability Standard project as high, medium, low, or pending technical committee input. | 2017-01
Note 9 | 2018-2020 RSDP | 2017-03
Note 10 | 2019-2021 RSDP (Draft) | 2017-04
2017-05
2017-07
2018-01
2018-02
2018-03

## Template (hidden)
Project | Test | [5 empty] | Home
Project Name | Test
Status | SAR
Comments | Test Comment
Deliverable | Test-001-1
Deadline | Test 1, 2016
Priority in RSDP, click to see applicable Footnote | Test Priority
P81 Req (2013) | Test P81
Number of Directives | Test Directives
No. of Guidances (see Note 2) | Test Guidance
Directionally consistent with IERP findings (See Note 5) | Test IERP
Developer | Test Developer
PMOS Liaison | Test PMOS
Affected Standards | Test Affected Standards
Last Updated
Scheduling Dates | Projected or Actual Start | Projected or Actual End | Baseline Start | Baseline End | No. of Days Ahead (Behind) | Reason for Change or Delay | Ballot or Other | Index
Nominations - SAR / PR | 2018-11-14 14:02 | 2018-11-28 14:02 | 2018-11-21 14:02 | 2018-12-05 14:02 | 7 |  |  | 1
Nominations - DT | 2018-12-19 14:02 | 2019-01-02 14:02 | 2018-12-26 14:02 | 2019-01-09 14:02 | 7 |  |  | 2
QR - Quality Review | 2019-01-23 14:02 | 2019-02-06 14:02 | 2019-01-30 14:02 | 2019-02-13 14:02 | 7 |  |  | 3
SP1 - SAR/PR/WP Posting 1 | 2019-02-27 14:02 | 2019-03-29 14:02 | 2019-03-06 14:02 | 2019-04-05 14:02 | 7 |  |  | 4
SP2 - SAR/PR/WP Posting 2 | 2019-04-19 14:02 | 2019-05-19 14:02 | 2019-04-26 14:02 | 2019-05-26 14:02 | 7 |  |  | 5
CP1 - Comment Period 1 | 2019-06-09 14:02 | 2019-07-09 14:02 | 2019-06-16 14:02 | 2019-07-16 14:02 | 7 |  |  | 6
CP2 - Comment Period 2 | 2019-07-30 14:02 | 2019-08-29 14:02 | 2019-08-06 14:02 | 2019-09-05 14:02 | 7 |  |  | 7
CIB - Com/Ballot 1 (Initial) | 2019-09-19 14:02 | 2019-11-03 14:02 | 2019-09-26 14:02 | 2019-11-10 14:02 | 7 |  |  | 8
CAB - Com/Add Ballot 2 | 2019-11-24 14:02 | 2020-01-08 14:02 | 2019-12-01 14:02 | 2020-01-15 14:02 | 7 |  |  | 9
CAB - Com/Add Ballot 3 | 2020-01-29 14:02 | 2020-03-14 14:02 | 2020-02-05 14:02 | 2020-03-21 14:02 | 7 |  |  | 10
CAB - Com/Add Ballot 4 | 2020-04-04 14:02 | 2020-05-19 14:02 | 2020-04-11 14:02 | 2020-05-26 14:02 | 7 |  |  | 11
CAB - Com/Add Ballot 5 | 2020-06-09 14:02 | 2020-07-24 14:02 | 2020-06-16 14:02 | 2020-07-31 14:02 | 7 |  |  | 12
FB - Final Ballot | 2020-08-14 14:02 | 2020-08-24 14:02 | 2020-08-21 14:02 | 2020-08-31 14:02 | 7 |  |  | 13
PTB - Present to BOT | 2020-09-14 14:02 | 2020-09-16 14:02 | 2020-09-21 14:02 | 2020-09-23 14:02 | 7 |  |  | 14
Filing - Filing with Regulators | 2020-10-07 14:02 | 2020-10-10 14:02 | 2020-10-14 14:02 | 2020-10-17 14:02 | 7 |  |  | 15
PT - Post Approval Training | 2020-10-31 14:02 | 2020-11-03 14:02 | 2020-11-07 14:02 | 2020-11-10 14:02 | 7 |  |  | 16
PTS Change Control
Reason for Update | Date | Notes
Formulas:
Test = +[Projected or Actual End, row above]+21
Projected or Actual End = +[Test]+14
Baseline Start = +[Test]+7
Baseline Start = +[Baseline End, row above]+21
Baseline End = +[Baseline Start]+14
Note on B19: Add the new project, then goto the dashboard and construct the project with conditional formatting. Change only this date as needed for testing conditional formatting of new projects. Delete this note wihen finished and associated dates, then fill in with appropriate project dates.

## Lookup Lists (hidden)
LOOKUP LISTS |  |  | Home
Delays | Status | Periods
Additional Outreach | Approved | Nominations - SAR / PR
Baseline Reset | Archived | Nominations - DT
Change in Approach | Filed | QR - Quality Review
Expanded Scope | Inactive | SP1 - SAR/PR/WP Posting 1
Missed SC Delivery | Nominations | SP2 - SAR/PR/WP Posting 2
Not needed | Nominations & SAR | CP1 - Comment Period 1
Other | On Hold | CP2 - Comment Period 2
Regulatory Meeting | Other | CIB - Com/Ballot 1 (Initial)
Schedule too Constrictive | Pending Board Adoption | CAB - Com/Add Ballot 2
Team Availability | Pending Regulatory Approval | CAB - Com/Add Ballot 3
x-Future | Pending Regulatory Filing | CAB - Com/Add Ballot 4
x-Future | Pending SC Action | CAB - Com/Add Ballot 5
x-Future | Posted | FB - Final Ballot
x-Future | Responding to Comment | PTB - Present to BOT
| SAR / PR / WP | Filing - Filing with Regulators
| SDT Development | PT - Post Approval Training
Standing Review Team
Working to Additional Ballot
Working to Comment Posting
Working to Final Ballot
Working to Initial Ballot
X-Future
X-Future
X-Future