## Project Plan and Gantt
Project Management Dashboard
Project Name: | [Name]
Report Date | [Date]
Project Status | On track
Completed | 27%
Tasks | Assigned To | Priority | Status
Set kick-off meeting | Alex B. |  | Complete
Agree on objectives | Frank C. | ★ | Complete
Detailed Reqs. | Jacob S. |  | Complete
Hardward Reqs. | Jacob S. | ★ | Overdue
Final Resource Plan | Jacob S. |  | In progress
Staffing | Alex B. | ★ | In progress
Techincal Reqs. | Frank C. |  | Not started
Testing | Kennedy K. | ★ | Not started
Dev. Complete | Jacob S. | ★ | Not started
Hardware Config. | Alex B. |  | Not started
System Testing | Kennedy K. | ★ | Not started
Launch
Smartsheet SightsTM give your team the ability to work smarter, with visibility into work as it's getting done.
Interested in trying Smartsheet to manage your projects? Click here to start your free 30-day trial today.

## Notes
Task Table
Tasks | Assigned To | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2015-09-02 | 2015-09-03 | 1 | Complete
Agree on objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2015-09-07 | 2015-09-12 | 5 | Complete
Hardward Reqs. | Jacob S. | 2015-09-09 | 2015-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4 | In progress
Staffing | Alex B. | 2015-09-16 | 2015-09-17 | 1 | In progress
Techincal Reqs. | Frank C. | 2015-09-17 | 2015-09-21 | 4 | Not started
Testing | Kennedy K. | 2015-09-24 | 2015-10-02 | 8 | Not started
Dev. Complete | Jacob S. | 2015-10-02 | 2015-10-05 | 3 | Not started
Hardware Config. | Alex B. | 2015-10-05 | 2015-10-07 | 2 | Not started
System Testing | Kennedy K. | 2015-10-06 | 2015-10-09 | 3 | Not started
Launch |  | 2015-10-09 | 2015-10-10 | 1
Percentage of Tasks Complete
Complete | 27.27%
Overdue | 9.091%
In progress | 18.18%
Not Started | 45.45%
Budget
Planned | 80000
Actual | 50000
Pending Items
Decisions | 5
Actions | 2
Change Requests | 4