## START
ABOUT THIS TEMPLATE
Track Project Parameters, Project Details, and Project Totals in this Event Planning Tracker workbook.
Enter information in Project Parameters worksheet to update column charts, and in Project Details worksheet. PivotTable in Project Totals worksheet is automatically updated.
Fill in Company Name in Parameters worksheet and it will automatically be updated in other worksheets.
Note:
Additional Instructions have been provided in column A of each worksheet in EVENT PLANNING TRACKER workbook. This text has been intentionally hidden. To remove text, select column A, then select DELETE. To unhide text, select column A, then change font color.
To learn more about tables in worksheets, press SHIFT and then F10 within a table, select the TABLE option, and then select ALTERNATIVE TEXT.

## PROJECT PARAMETERS
Create Project Parameters in this worksheet. Enter Company Name in cell at right. Helpful instructions are in cells in this column. Arrow down to get started. | Company Name
Title of this worksheet is in cell at right. | Event Management Project Tracker
Confidentiality message is in cell at right. | Company Name Confidential
Tip is in cell at right. | Shaded cells are calculated for you. You do not need to enter anything into them.
Enter details in Parameters table starting in cell at right. Next instruction is in cell A12. | PROJECT TYPE | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | Total
| Event strategy development | 20% | 10% | 60% | 0% | 0% | 10% | 100%
| Event planning | 20% | 50% | 10% | 10% | 0% | 10% | 100%
| Event design | 20% | 20% | 0% | 50% | 0% | 10% | 100%
| Event logistics | 20% | 60% | 0% | 0% | 10% | 10% | 100%
| Event staffing | 20% | 10% | 0% | 0% | 60% | 10% | 100%
| Event assessment | 20% | 20% | 20% | 20% | 0% | 20% | 100%
Enter Blended Rates in cells at right, cells C12 through H12. Next instruction is in cell A14. | Blended rates | 180 | 120 | 150 | 100 | 80 | 60
Column chart showing planned versus actual cost is in cell at right, and column chart showing planned versus actual hours is in cell F14. |  |  |  |  | Column chart showing planned versus actual hours is in this cell.
|  | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
| PLANNED COST | 54000 | 52200 | 24000 | 29000 | 13200 | 9000
| ACTUAL COST | 54360 | 51540 | 25650 | 28900 | 13400 | 9060
| PLANNED HOURS | 300 | 290 | 133.3333 | 161.1111 | 73.3333 | 50
| ACTUAL HOURS | 302 | 286.3333 | 142.5 | 160.5556 | 74.4444 | 50.3333
Column chart showing planned versus actual cost is in this cell.

## PROJECT DETAILS
Create Project Details in this worksheet. Company Name is automatically updated in cell at right. Helpful instructions are in cells in this column. Arrow down to get started. | Company Name
Title of this worksheet is in cell at right. | Event Management Project Tracker
Confidentiality message is in cell at right. | Company Name Confidential
Enter information in Project Details table starting in cell at right. INFO To add a row in table at right, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or press SHIFT+F10 key where you want the row inserted and select Insert ¦ Table Rows Above/Below. Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results. | PROJECT NAME | PROJECT TYPE | ESTIMATED START | ESTIMATED FINISH | ACTUAL START | ACTUAL FINISH | ESTIMATED WORK | ACTUAL WORK | ESTIMATED DURATION | ACTUAL DURATION | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
| Project 1 | Event strategy development | 2018-06-09 | 2018-08-07 | 2018-06-29 | 2018-09-03 | 200 | 220 | 58 | 64 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7920 | 2640 | 19800 | 0 | 0 | 1320
| Project 2 | Event planning | 2019-06-25 | 2019-07-27 | 2018-07-15 | 2019-08-25 | 400 | 390 | 32 | 400 | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 14040 | 23400 | 5850 | 3900 | 0 | 2340
| Project 3 | Event design | 2020-07-12 | 2020-09-19 | 2025-08-07 | 2025-10-10 | 500 | 500 | 67 | 63 | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 18000 | 12000 | 0 | 25000 | 0 | 3000
| Project 4 | Event logistics | 2021-07-30 | 2021-09-28 | 2021-09-14 | 2021-11-13 | 150 | 145 | 58 | 59 | 5400 | 10800 | 0 | 0 | 1200 | 900 | 5220 | 10440 | 0 | 0 | 1160 | 870
| Project 5 | Event staffing | 2022-08-11 | 2022-08-21 | 2022-09-14 | 2022-09-25 | 250 | 255 | 10 | 11 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 9180 | 3060 | 0 | 0 | 12240 | 1530
| TOTAL | [5 empty] | 1500 | 1510 | 225 | 597
INFO
To add a row, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or right-click where you want the row inserted and select Insert | Table Rows Above/Below.
Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results.
To delete this info tip, select any edge and press Delete.

## PROJECT TOTALS
Get Project Totals in this worksheet. Company Name is automatically updated in cell at right. Helpful instructions are in cells in this column. Arrow down to get started. | Company Name
Title of this worksheet is in cell at right. | Event Management Project Tracker
Confidentiality message is in cell at right. | Company Name Confidential
PivotTable starting in cell at right is automatically updated. INFO To refresh PivotTable at right, select it (any cell within the PivotTable), on the PIVOTTABLE TOOLS ¦ ANALYZE ribbon tab select Refresh Or press SHIFT+F10 key in any cell in the PivotTable, and then select Refresh. | PROJECT NAME | ACCOUNT MANAGER ESTIMATE | PROJECT MANAGER ESTIMATE | STRATEGY MANAGER ESTIMATE | DESIGN SPECIALIST ESTIMATE | EVENT STAFF ESTIMATE | ADMIN STAFF ESTIMATE | ACCOUNT MANAGER ACTUAL | PROJECT MANAGER ACTUAL | STRATEGY MANAGER ACTUAL | DESIGN SPECIALIST ACTUAL | EVENT STAFF ACTUAL | ADMIN STAFF ACTUAL
| Project 1 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7920 | 2640 | 19800 | 0 | 0 | 1320
| Project 2 | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 14040 | 23400 | 5850 | 3900 | 0 | 2340
| Project 3 | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 18000 | 12000 | 0 | 25000 | 0 | 3000
| Project 4 | 5400 | 10800 | 0 | 0 | 1200 | 900 | 5220 | 10440 | 0 | 0 | 1160 | 870
| Project 5 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 9180 | 3060 | 0 | 0 | 12240 | 1530
| Grand Total | 54000 | 52200 | 24000 | 29000 | 13200 | 9000 | 54360 | 51540 | 25650 | 28900 | 13400 | 9060
INFO
This PivotTable will not refresh automatically. To refresh it, select it (any cell within the PivotTable), on the PIVOTTABLE TOOLS | ANALYZE ribbon tab press Refresh. Or right-click any cell in the PivotTable and select Refresh.
To delete this info tip, select any edge and press Delete.