## Commentary
Revision History
| Jan 2019 | The instructions were expanded to address protecting and unprotecting sheets.
| July 2018 | A line was added to the lookup table so the workbook works in Ontario with either the old Construction Lien Act or the new Construction Act. The lookup tables have been expanded with parameters from the other jurisdictions in Canada besides Ontario for use on projects in those jurisdictions. In addition the labels on the tabs have been enhanced to reflect the terminology/parameters of the selected jurisdiction.
| May 2017 | The Certificate For Payment was reorganized to better reflect that the certification is of the value of the work completed to date and the amount owing to the contractor this payment period. The calculation are provided for convenience and information, and are themselves not being certified.
| May 2017 | The calculation of statutory holdback has been changed to explicitly show separate line items for basic and finishing holdback. This requires one additional step by the user for projects in Ontario: to enter the amount of work complete at Substantial Performance (In the labelled cell that is part of the Trial Certificate of Substantial Performance). It does however permit the workbook to be used for projects being done in other provinces or territories where there may be no finishing holdback or a different calculation may be required.
Commentary on Schedules of Values
BY ALLEN HUMPHRIES, Architect (Retired)
The schedule of values for a project as described in CCDC 24: A Guide to Administrative Support Documents is for the purpose of facilitating the consultant’s review of the application for payment. In CCDC 2 2008 GC 5.2, paragraphs 5.2.4 to 5.2.6 set forth the requirements for the schedule of values. It requires the contractor to prepare and submit a schedule of values to the consultant before the first application for payment. The consultant must review and either accept the schedule or request changes.
The fewer items in the schedule, the less effort required of the contractor each month in updating the schedule to reflect the current status of the work. It is easiest for the contractor to provide a breakdown based on the value of the subcontracts. It is unusual for the contractor in the first instance to provide the level of detail needed to facilitate the consultant’s review of the applications for payment.
The optimum breakdown of any item of work in order to facilitate review of an application for payment depends on the nature of the item of work.
  1. If the materials may be delivered in bulk before being installed, the labour and material costs should be identified separately in the schedule. E.g. hollow metal doors and frames, and installation/labour costs.
  2. If a subcontract consists of different items of work with materials of different values or quantities, the materials should be identified separately. E.g. porcelain floor tiles and ceramic wall tiles.
  3. If a subcontract consists of different items of work that will be done sequentially, the materials and the labour involved should be identified separately. E.g. ceiling grids, ceiling grid labour, ceiling tiles, and ceiling tile labour.
One item that is often overlooked is the value assigned to close-out documents (as-built drawings, warrantees, operation and maintenance manuals, etc.). It is often difficult get the close-out documents in a timely manner, and the end of a project is not the time to determine how much the documents are worth. The value of the close-out documents should be determined at the beginning of the project. This will avoid arguments later.
The value assigned will vary with both the size and complexity of the project. The close-out documents for a warehouse shell will be simpler than for a hospital or for a data centre. The value assigned should be low enough to permit the contractor to achieve substantial performance without the close-out documents, but high enough that deemed completion cannot be reached without them. This will encourage the contractor to submit the close-out documents in a timely manner in order to acheive deemed completion and have the finishing holdback released.
The total dollar value at the bottom of the schedule of values must match the contract value and the breakdown by discipline (Architectural, Structural, Mechanical, Electrical) should match the values on the bid form, individual items may vary from those on the bid form. This may occur for example, where a line item in the schedule includes the work of different trades, or work by the contractor’s own forces, where one trade supplies items for installation by another, or where subcontract values are adjusted to reflect a trade’s contribution to the value of close-out documents.
Although it is the contractor’s responsibility to prepare the schedule of values, a sample schedule of values can be included in the project specifications (00 43 73 Proposed Schedule of Values Form) to indicate the desired format, items of particular interest, the general level of detail expected and the value of the close-out documents. Of course, the engineering consultants should be asked to provide input about the desired breakdown for their scopes of work. Including a draft schedule of values in the specification provides a basis for discussion at the project kick-off meeting and can reduce the effort needed to come to an agreement with the contractor on an acceptable schedule of values during project start up.
Since the schedule of values includes much repetitive arithmetic, the writer highly recommends that the consultant create a schedule of values for each project using spreadsheet software or a contract administration software package. When an application for payment is received, the percent complete for each line item can be easily entered in the software, and the totals compared with those of the contractor to determine if there are any calculation errors. Doing so has saved the writer hours of effort tracking down mistakes in applications for payment. A sample workbook is available for download from the Management of the Project pages of the OAA web site.
The inclusion of change orders is a two-stage process since they exist before they are approved and may not be approved in the sequence they were created in. As change orders are issued, they should be recorded in the schedule of values. Once the change order is approved (signed by all parties), it should only then be included in the contract value. Where a change order contains only one item of work, it can be entered as a single line item in the schedule. Where a change order contains several items of work or aggregates several proposed changes, it is beneficial to include a line item for each item of work in the change order to facilitate review of the application for payment.
A properly set out schedule of values will make the evaluation of the status of progress easier to determine and any amendments made by the consultant easier to explain to the owner and the contractor.
R9 2019-01-24

## Project Info
Schedule of Values/Certificate for Payment workbook |  |  |  | Rev. 2019 01
History
The version was updated to work with the new Construction Act, and at the same time was expanded to work with the lien legislation of the other jurisdictions in Canada. It is made available through the OAA's PAR committee.
The first public version was made available through the OAA's CCA committee. It worked with the Construction Lien Act of Ontario only.
The original version of this workbook was developed 30 years ago to assist the author in checking applications for payment.
Initial Instructions:
0 | The proper functioning of this workbook depends on the operation of macro programming written using Visual Basic for Applications (VBA). The VBA language is a part of the applications in the Microsoft Office suite. Unless macros are enabled, this workbook will not function properly.
If used with malicious intent, VBA macros can be used to attack or damage computer files. The macros used in this workbook copy tabs and information between tabs. They do not access any other file or the internet, nor have they caused any known issues with other programs.
To avoid anyone easily tampering with the macros and circulating an infected file, access to the macros is protected. To protect yourself, you should download a copy of the workbook directly from the OAA web site. This also ensures you have the latest version of the workbook complete with any bug fixes and enhancements.
Before this workbook will function, you wil need to enable macros by clicking on the button below the menu bar or by declaring this file to be a trusted file or by putting it in a trusted folder.
When protected, you should be able to enter data into any of the green shaded cells. It is recommended that you protect the sheets to avoid accidentally changing or deleting formulas.
1 | Fill in the initial information in the green shaded cells below.
| Client Name | Favourite Client Company
| Client Address 1 | Client Address 1
| Client Address 2 | Client Address 2
| Client Representative | Favourite Person
| Building Permit Number | 18 111999 BLD 00 BA
| Project Number | 18.32001.00
| Project Name | Award Winner
| Project Type | Sustainable Office
| Consultant | Visionary Architects
| Consultant Address 1 | Address line 1
| Consultant Address 2 | Address line 2
| Consultant Telephone | (999) 123-4567
| Consultant Fax | (000) 987-6543
| Contractor | Quality Contractors Inc.
| Contract Amount | 1234567.89
| Start of First Payment Period | 2018-07-01
| Year | 2018 | YYYY
| Month | 7 | MM
| Day | 1 | DD
| Province | Ontario
| Applicable Legislation | Construction Act, Ontario
| Basic Holdback % | 10%
| Finishing Holdback % | 10%
| Basis of Holdback Release | -
| Tax Rate | 13%
| Tax Type | HST
2 | Insert or delete line items as needed to reflect the current project in the schedule of values on the "App For Payment-Template" tab.
3 | If the sheet is protected, go to the Review tab and click on Unprotect Sheet.
4 | Ensure the formulas are copied into the newly inserted lines.
5 | Repeat across all columns.
6 | Use the Record Docs tab to determine an appropriate value for the entire record documents.
7 | Divide the total as appropriate across the various disciplines.
8 | If not already included as part of the bid documents, send a PDF copy of the schedule of values portion of the worksheet
to the Contractor as a template for their use in submitting the contract breakdown.
Usage Instructions:
9 | Copy the agreed upon contract breakdown values provided by the Contractor into the "Contract Amount" column.
10 | When complete, go to the Review tab and click on Protect Sheet.
11 | Click on the "Create a new Schedule of Values" button to create one.
12 | Enter the percent complete into the green shaded cells in the "% to Date" column.
13 | Enter any holdback released or deficiency amounts into the green boxes in the Certificate section.
13 | Compare the totals and certificate values with the Contractor's application for payment.
If all agrees, prepare a Certificate For Payment.
If there are differences, advise the Contractor and attempt to resolve them.
14 | Submit a PDF of the schedule of values portion of the worksheet with the Certificate for Payment.
15 | Convert the Date Issued field on the schedule of values from a formula to a date value (Copy and Paste values)
Change Orders:
16 | Change orders are handled the same way as line items in the schedule of values section with one major difference.
The difference allows you to enter the change order information when it is issued, but not have it affect the contract amount until approved.
There is a formula in the contract amount column
The change order amount is initially entered in the green shaded "CO Amount" column.
When the change order is signed by the Owner and Contractor, an entry is made in the green shaded "Approved" column.
This causes the amount to be displayed in the "Contract Amount" column.
Substantial Performance:
17 | The substantial performance section below the schedule of values section automatically calculates and displays the status of the project.
When substantial performance has been achieved, enter the value of the work completed at substantial performance in the cell indicated.
Doing so allows the finishing holdback to be calculated at a different rate where required by the jurisdiction of the place of the work.
Deemed Completion:
18 | The deemed completion section below the substantial performance section automatically calculates and displays the status of the project.
Deficiency Retainage
19 | The Deficiency Retainage line item on the certificates for payment is provided for those who use this method.
It is preferable to reflect the value to correct deficient work in the appropriate line items of the schedule of values
so that you are only certifying the value of work completed in accordance with the contract documents.
The latter method makes it explicit to the general contractor and the sub-contractors which items are deficient.
It also makes it easier to adjust the schedule of values as the deficiencies are completed.
Disclaimer
This sample workbook was developed by an architect for use on projects he managed, and is made freely available for your use. It comes with no guarantee or warrantee, express or implied. Use it at your own risk.
There is not a team of programmers developing or supporting this document, so don’t expect frequent updates. If you find it useful, let the OAA Practice Advisory Services (PAS) know. If you think a revision or enhancement would make the document more useful to most users, suggest it to PAS. If you find an error, tell PAS about it so it can be fixed.
As with any software, you should check the calculations manually or by using another tool until you are confident that the software produces the correct results. This is particularly true following substantial changes such as those made for this latest version. Extensive testing of all the possible combinations of the new jurisdictions and parameters has not been possible with the resources available.

## Record Docs
Proposed Value of As-Builts/Close-out Documents
Hide these 2 columns
| Initial Contract Value: |  |  | 1234567.89
Calculations of value based on percentage of initial contract value
Calc 1 | Initial Contract Value Range | Limits | Percentage | Percentage | As-Built Value | Rounded
| Less than $150000 | 150000 | 3% | 3%
| From $150000 to $300000 | 300000 | 2% | 2%
| From $300000 to $750000 | 750000 | 1% | 1%
| Greater than $750000 |  | 0.5% | 0.5%
0.5%
|  |  |  | 0.5% | 6172.8394 | 6180
Calc 2 | Initial Contract Value | Differential |  | Percentage | As-Built Value | Rounded
| On the first $150000 | 150000 | 3% | 3% | 4500
| On the next $150000 | 150000 | 2% | 2% | 3000
| On the next $450000 | 450000 | 1% | 1% | 4500
| On the remaining $484567.89 | 484567.89 | 0.5% | 0.5% | 2422.8394
[5 empty] | 14422.8394 | 14430
If this value exceeds $34,691.36 then Substantial Performance/Completion cannot be achieved without Close-out Document completion.
If this value is less than $5,000.00 then Deemed Completion can be achieved without Close-out Documents.
The appropriate record document value will vary depending on the nature of the project. Enter the desired value in the Schedule of Values before sending to the Contractor.
| Substantial Performance: |  |  |  |  | Based on the Construction Act, Ontario
| Initial Contract Amount |  |  | 1234567.89
| 3% on 1st $1000000 |  |  | 1000000 | 3% | 30000
| 2% on next $1000000 |  |  | 234567.89 | 2% | 4691.36
| 1% on remainder |  |  | 0 | 1% | 0
| Maximum outstanding per Act |  |  |  |  | 34691.36
| Deemed Completion: |  |  |  |  | Based on the Construction Act, Ontario
| Initial Contract Amount |  |  | 1234567.89
| A % of contract amount |  |  |  | 1% | 12345.68
| B Construction Act, Ontario |  |  |  |  | 5000
(Section 2 subsection (3) limit)
| Maximum outstanding per Act (lesser of A and B) |  |  |  |  | 5000
To change any of the calculation parameters, unhide columns C and D.
Note
The purpose of the schedule of values is to assist the architect in evaluating the value of the work done to date in response to an application for payment so a certificate for payment may be prepared.
According to CCDC 24, it is the contractors responsibility to prepare a schedule of values and submit it to the architect for review and approval prior to the submission of the first application for payment.
This typically resulted in several rounds of revision and correction between the architect and contractor. To reduce the time spent on this exercise, the author choose to include a sample schedule of values in the bid documents as a guide to the contractor of how the architect expected the contract to be broken down.
Part of this process included adding line items for the value of the close out documents. This avoids arguments at the end of the project about the value assigned, and allows the contractor to encourage the trades to do their bit.
This process was generally accepted and reduced the amount of time spent coming to an agreement on an appropriate schedule of values.

## App For Payment-Template
Favourite Client Company | [6 empty] | Document 00 62 73
Project Name: | Award Winner - Sustainable Office | [5 empty] | SCHEDULE OF VALUES
Project Number: | 18.32001.00 |  |  |  |  | Application for Payment #: | 0
Consultant: | Visionary Architects |  |  |  |  | Issue Date: | 2021-06-16 12:49
Contractor: | Quality Contractors Inc. |  |  |  |  | For Period Ending: | 2018-07-31
Spec. Section | Item | Contract Amount | % to Date | Previous Amount | Amount This Draw | Completed to Date | Balance to Complete
General | Insurance | 0 | 0% | 0 | 0 | 0 | 0
| Bonding | 0 | 0% | 0 | 0 | 0 | 0
| Mobilization | 0 | 0% | 0 | 0 | 0 | 0
| Supervision | 0 | 0% | 0 | 0 | 0 | 0
| Disposal | 0 | 0% | 0 | 0 | 0 | 0
| Labour | 0 | 0% | 0 | 0 | 0 | 0
| General Conditions | 0 | 0% | 0 | 0 | 0 | 0
01 73 29 | Cutting & Patching | 0 | 0% | 0 | 0 | 0 | 0
01 77 00 | Project Record Docs (Manuals/Docs/ As-builts) | 0 | 0% | 0 | 0 | 0 | 0
03 33 00 | Cast-in-Place Concrete (below grade) | 0 | 0% | 0 | 0 | 0 | 0
03 33 00 | Cast-in-Place Concrete (above grade) | 0 | 0% | 0 | 0 | 0 | 0
03 45 00 | Precast Concrete | 0 | 0% | 0 | 0 | 0 | 0
04 21 13 | Brick Masonry | 0 | 0% | 0 | 0 | 0 | 0
04 22 00 | Concrete Unit Masonry | 0 | 0% | 0 | 0 | 0 | 0
05 12 00 | Structural Steel Framing | 0 | 0% | 0 | 0 | 0 | 0
05 31 00 | Steel Decking | 0 | 0% | 0 | 0 | 0 | 0
05 50 00 | Metal Fabrications | 0 | 0% | 0 | 0 | 0 | 0
05 73 00 | Handrail Railings | 0 | 0% | 0 | 0 | 0 | 0
06 10 00 | Rough Carpentry | 0 | 0% | 0 | 0 | 0 | 0
06 40 23 | Architectural Woodwork | 0 | 0% | 0 | 0 | 0 | 0
06 90 00 | General Installations | 0 | 0% | 0 | 0 | 0 | 0
07 24 15 | EIFS | 0 | 0% | 0 | 0 | 0 | 0
07 51 00 | Roofing | 0 | 0% | 0 | 0 | 0 | 0
07 62 00 | Sheet Metal Flashing & Trim | 0 | 0% | 0 | 0 | 0 | 0
07 92 00 | Joint Sealants | 0 | 0% | 0 | 0 | 0 | 0
08 11 13 | HM Doors/Frames | 0 | 0% | 0 | 0 | 0 | 0
08 11 16/08 43 29 | Aluminum Sliding Doors | 0 | 0% | 0 | 0 | 0 | 0
08 41 13 | Aluminum Framed Entrances | 0 | 0% | 0 | 0 | 0 | 0
08 51 13 | Aluminum Windows | 0 | 0% | 0 | 0 | 0 | 0
08 71 00 | Door Hardware Supply | 0 | 0% | 0 | 0 | 0 | 0
08 81 00/08 83 13 | Glass Glazing/Mirrors | 0 | 0% | 0 | 0 | 0 | 0
08 87 00 | Glazing Surface Film | 0 | 0% | 0 | 0 | 0 | 0
09 21 16 | Gypsum Board Assemblies | 0 | 0% | 0 | 0 | 0 | 0
09 51 00 | Acoustical Ceilings | 0 | 0% | 0 | 0 | 0 | 0
09 65 00 | Resilient Flooring | 0 | 0% | 0 | 0 | 0 | 0
09 68 13 | Tile Carpeting | 0 | 0% | 0 | 0 | 0 | 0
09 90 00 | Painting & Coating | 0 | 0% | 0 | 0 | 0 | 0
09 91 00 | Painting | 0 | 0% | 0 | 0 | 0 | 0
10 21 13.13 | Metal Toilet Compartments | 0 | 0% | 0 | 0 | 0 | 0
10 26 13 | Corner Guards | 0 | 0% | 0 | 0 | 0 | 0
10 26 16 | Bumper Guards | 0 | 0% | 0 | 0 | 0 | 0
11 52 13 | Projection Screens | 0 | 0% | 0 | 0 | 0 | 0
11 52 23 | TV/VCR Mount | 0 | 0% | 0 | 0 | 0 | 0
12 48 16 | Entrance Floor Grilles | 0 | 0% | 0 | 0 | 0 | 0
12 24 13 | Roller Shades | 0 | 0% | 0 | 0 | 0 | 0
32 12 16 | Asphalt Paving | 0 | 0% | 0 | 0 | 0 | 0
32 31 13 | Chain Link Fencing | 0 | 0% | 0 | 0 | 0 | 0
| Architectural subtotal: | 0 | 0% | 0 | 0 | 0 | 0
21 00 00 | Fire Supression - Labour | 0 | 0% | 0 | 0 | 0 | 0
| Fire Supression - other | 0 | 0% | 0 | 0 | 0 | 0
| Piping | 0 | 0% | 0 | 0 | 0 | 0
| Supports | 0 | 0% | 0 | 0 | 0 | 0
| Sprinkler heads | 0 | 0% | 0 | 0 | 0 | 0
| Fire Stopping/Sealants | 0 | 0% | 0 | 0 | 0 | 0
| Manuals/Documentation/As-builts | 0 | 0% | 0 | 0 | 0 | 0
22 00 00 | Plumbing - Labour | 0 | 0% | 0 | 0 | 0 | 0
| Plumbing - other | 0 | 0% | 0 | 0 | 0 | 0
| Piping | 0 | 0% | 0 | 0 | 0 | 0
| Insulation | 0 | 0% | 0 | 0 | 0 | 0
| Fixtures | 0 | 0% | 0 | 0 | 0 | 0
| Manuals/Documentation/As-builts | 0 | 0% | 0 | 0 | 0 | 0
23 00 00 | HVAC - Labour | 0 | 0% | 0 | 0 | 0 | 0
| Roof top units | 0 | 0% | 0 | 0 | 0 | 0
| Chillers | 0 | 0% | 0 | 0 | 0 | 0
| Condensors | 0 | 0% | 0 | 0 | 0 | 0
| Ductwork | 0 | 0% | 0 | 0 | 0 | 0
| Grilles/diffusers | 0 | 0% | 0 | 0 | 0 | 0
| Controls | 0 | 0% | 0 | 0 | 0 | 0
| Clean up | 0 | 0% | 0 | 0 | 0 | 0
| Installation | 0 | 0% | 0 | 0 | 0 | 0
| Insulation | 0 | 0% | 0 | 0 | 0 | 0
| Baseboard Heaters | 0 | 0% | 0 | 0 | 0 | 0
| Air Balancing | 0 | 0% | 0 | 0 | 0 | 0
| Manuals/Documentation/As-builts | 0 | 0% | 0 | 0 | 0 | 0
| Mechanical subtotal: | 0 | 0% | 0 | 0 | 0 | 0
26 00 00 | Electrical - Labour | 0 | 0% | 0 | 0 | 0 | 0
| Electrical - other | 0 | 0% | 0 | 0 | 0 | 0
| Lighting - Rough-in |  | 0% | 0 | 0 | 0 | 0
| Lighting Fixtures | 0 | 0% | 0 | 0 | 0 | 0
| Transformers | 0 | 0% | 0 | 0 | 0 | 0
| Switchgear | 0 | 0% | 0 | 0 | 0 | 0
| Panels | 0 | 0% | 0 | 0 | 0 | 0
| Power - Rough-in | 0 | 0% | 0 | 0 | 0 | 0
| Devices | 3000000 | 0% | 0 | 0 | 0 | 3000000
| Manuals/Documentation/As-builts | 0 | 0% | 0 | 0 | 0 | 0
0
27 10 00 | Data Cabling | 0 | 0% | 0 | 0 | 0 | 0
27 51 19 | Sound Masking | 0 | 0% | 0 | 0 | 0 | 0
| Electrical subtotal: | 3000000 | 0% | 0 | 0 | 0 | 3000000
| Base Contract subtotal: | 3000000 | 0% | 0 | 0 | 0 | 3000000
The base contract subtotal doesn't match the amount on the Project Info tab.
Cash Allowances:
1 |  | 0 | 0% | 0 | 0 | 0 | 0
2 |  | 0 | 0% | 0 | 0 | 0 | 0
3 |  | 0 |  | 0 | 0 | 0 | 0
| Cash Allowance subtotal: | 0 | 0% | 0 | 0 | 0 | 0
| Contract subtotal: | 3000000 | 0% | 0 | 0 | 0 | 3000000
Issued Change Orders: | [7 empty] | Approved | CO Amount
1 | CO title | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
2 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
3 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
4 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
5 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
6 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
7 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
8 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
9 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
10 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
| Change Order subtotal: | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
| Contract amount: | 3000000 | 0% | 0 | 0 | 0 | 3000000
Issued Change Directives: | [7 empty] | Approved | Undisputed Amount | Estimated CD Amount
1 | CD title | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
2 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
3 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
4 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
5 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
6 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
7 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
8 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
9 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| Change Directive subtotal: | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
| Contract amount: | 3000000 | 0% | 0 | 0 | 0 | 3000000
Trial Certificate For Payment: |  | - |  | <-- Select certificate qualifier
|  | Contract Amount | % to Date | Previous Amount | Amount This Draw | Completed to Date | Balance to Complete
| Sub Total | 3000000 | 0% | 0 | 0 | 0 | 3000000 | asdf
| HST at 13% | 390000
| Total Contract | 3390000
Deficiency retainage
|  | Basic holdback of | 10% |  |  | 0
|  | Finishing holdback of | 10% |  |  | 0
|  | Current work less holdbacks |  |  |  | 0
|  | Holdback previously released |  |  | 0
|  | Holdback released this issue |  |  |  |  | 0
|  | Total holdback released |  |  |  | 0
|  | Payable to date |  |  |  | 0
|  | Previously payable (from payable to date on previous certificate) |  |  |  |  | <-enter value
|  | Payable this issue |  |  |  | 0
|  | HST payable | 13% |  |  | 0
[5 empty] | Total: | 0
[5 empty] | Adjustment to match invoice: | 0
[5 empty] | Total payable: | 0
Trial Certificate of Substantial Performance: |  |  |  | Based on the Construction Act, Ontario |  |  | yyyy-mm-dd
| Initial Contract Amount | 1234567.89 |  |  | Date of Publication:
| Revised Contract Amount | 3000000 |  |  | Lien Period: | 60 | days
| 3% on 1st $1000000 | 1000000 | 3% | 30000 | Expiry of Lien Period:
| 2% on next $1000000 | 1000000 | 2% | 20000
| 1% on remainder | 1000000 | 1% | 10000 | Release of Holdback:
| Maximum outstanding per lien act |  |  | 60000
| Balance to complete per Schedule of Values |  |  | 3000000 | Not Substantially performed before deferals
Amount agreed to be deferred
| Adjusted Balance to Complete |  |  | 3000000 | Not Substantially performed
| Margin |  |  | -2940000 | Leave blank until substantially performed:
| Sliding percentage: |  | 2% |  |  |  | 0
Holdback Released after Date of Publication of Certificate of Substantial Performance:
| Revised Contract Amount | 3000000
| A1 Basic holdback: | 0 | 10% | of the value of work completed to date. |  | 0
| A2 Finishing holdback: | 0 | 0%
0
| B Previously released: | 0
| C Holdback remaining: | 0
| Balance to Complete per schedule of values |  |  | 3000000
Trial Deemed Completion: |  |  |  | Based on the Construction Act, Ontario |  |  | yyyy-mm-dd
| Revised Contract Amount | 3000000 |  |  | Date Deemed Complete:
| A % of contract amount |  | 1% | 30000 | Lien Period: | 60 | days
| B Construction Act, Ontario |  |  | 5000 | Expiry of Lien Period:
(Section 2 subsection (3) limit)
| Maximum outstanding per lien act (lesser of A and B) |  |  | 5000 | Release of Finishing Holdback:
| Balance to Complete per schedule of values |  |  | 3000000 | Not Deemed Complete
Rev. 2019 01
Note on C141: This label shows on the Certificate for Payment
Note on F160: This line is provided to adjust the amount up or down to account for rounding errors.
Note on H168: If the lien period ends on a Saturday, Sunday, or Statutory Holiday, extend it to the next business day, & release holdback the day following.
Note on H195: If the lien period ends on a Saturday, Sunday, or Statutory Holiday, extend it to the next business day, & release holdback the day following.

## Certificates For Payment
Visionary Architects |  |  | Certificate for Payment |  | template | App For Payment-template | Enter the number of the Application for Payment for which you want to show the Certificate for Payment:
Address line 1 | [5 empty] | StartDate
Address line 2
Tel: (999) 123-4567 Fax: (000) 987-6543 | [5 empty] | 3
141
Project: | Award Winner |  | Certificate for Payment: | template |  | C141
Project Number: | 18.32001.00 |  | Select Certificate qualifier in cell C141 on the AfP tab before printing this certificate.
Owner: | Favourite Client Company |  | Issue Date: | 2021 06 16
Client Address 1
Client Address 2
Attention: | Favourite Person |  | File:
This is to certify that Quality Contractors Inc. has completed work and delivered products to the place of the work to date, to the value of $0.00 and is entitled to $0.00 for the period from July 01, 2018 to July 31, 2018.
By law, the amount certified is subject to reduction by the amount of any lien of which you have received written notice. The certificate is not negotiable, and is payable to the payee named in it. Issuance, payment, and acceptance are without prejudice to any rights of the Owner or Contractor under their contract.
The issue of this Certificate for Payment shall not be taken as a representation that the Consultant has made any examination to ascertain how and for what purpose the Contractor has used monies paid on account of the contract or that the Contractor has discharged the obligations imposed on him/her by law under the Worker's Compensation Act, or other applicable statutes, non-compliance with which may render the Client personaly liable for the Contractor's default.
Visionary Architects |  |  | Quality Contractors Inc.
Per:
Consultant's Signature: |  |  | Contractor's Acknowledgement
Date
Original Contract Amount |  | 1234567.89
Total Changes to Date |  | 0
Current Contract Amount |  | 1234567.89 | 1234567.89
Value of Work Finished |  | 0
Deficiency Retainage |  | 0
Statutory Holdback (basic) @ 10 % |  | 0
Statutory Holdback (finishing) @ 10 % |  | 0
Current Work less Holdbacks |  | 0 | 0
Holdback Previously Released |  | 0
Holdback Released This Issue |  | 0
Total Holdback Released |  | 0 | 0
Payable to Date |  |  | 0
Less Previously Payable |  |  | 0
Payable This Issue |  |  | 0
Applicable Taxes for Place of the Work HST @ 13 % |  |  | 0
Total Payable This Issue |  |  | 0

## Cert For Pay (Annual or Phased)
Visionary Architects |  |  | Certificate for Payment |  | template | App For Payment-template | Enter the number of the Application for Payment for which you want to show the Certificate for Payment:
Address line 1 | [5 empty] | StartDate
Address line 2
Tel: (999) 123-4567 Fax: (000) 987-6543 | [5 empty] | 3
141
Project: | Award Winner |  | Certificate for Payment: | template |  | C141
Project Number: | 18.32001.00 |  | Select Certificate qualifier in cell C141 on the AfP tab before printing this certificate.
Owner: | Favourite Client Company |  | Issue Date: | 2021 06 16
Client Address 1
Client Address 2
Attention: | Favourite Person |  | File:
This is to certify that Quality Contractors Inc. has completed work and delivered products to the place of the work to date, to the value of $0.00 and is entitled to $0.00 for the period from July 01, 2018 to July 31, 2018.
By law, the amount certified is subject to reduction by the amount of any lien of which you have received written notice. The certificate is not negotiable, and is payable to the payee named in it. Issuance, payment, and acceptance are without prejudice to any rights of the Owner or Contractor under their contract.
The issue of this Certificate for Payment shall not be taken as a representation that the Consultant has made any examination to ascertain how and for what purpose the Contractor has used monies paid on account of the contract or that the Contractor has discharged the obligations imposed on him/her by law under the Worker's Compensation Act, or other applicable statutes, non-compliance with which may render the Client personaly liable for the Contractor's default.
Visionary Architects |  |  | Quality Contractors Inc.
Per:
Consultant's Signature: |  |  | Contractor's Acknowledgement
Date
Original Contract Amount |  | 1234567.89
Total Changes to Date |  | 0
Current Contract Amount |  | 1234567.89 | 1234567.89
Value of Work Finished |  | 0
Deficiency Retainage |  | 0
Statutory Holdback @ 10 % |  | 0
Current Work less Holdbacks |  | 0 | 0
Holdback Previously Released |  | 0
Holdback Released This Issue |  | 0
Total Holdback Released |  | 0 | 0
Payable to Date |  |  | 0
Less Previously Payable |  |  | 0
Payable This Issue |  |  | 0
Applicable Taxes for Place of the Work HST @ 13 % |  |  | 0
Total Payable This Issue |  |  | 0

## Lookups
Project location: | Ontario
[6 empty] | ProvinceList |  |  |  | CfP_Purpose |  |  |  | HB_Release
[6 empty] | Ontario |  |  |  | - |  |  |  | -
[6 empty] | British Columbia |  |  |  | Progress Payment |  |  |  | Substantial Performance
[6 empty] | Alberta |  |  |  | Substantial Performance |  |  |  | Completion
[6 empty] | Saskatchewan |  |  |  | Release of Basic Holdback |  |  |  | Annual Release
[6 empty] | Manitoba |  |  |  | Release of Finishing Holdback |  |  |  | Phased Release
[6 empty] | Quebec |  |  |  | Release of Holdback
DOW | Name | Add to skip weekend |  |  |  | New Brunswick |  |  |  | Release of Holdback (Annual)
1 | Sunday | 1 |  |  |  | Nova Scotia |  |  |  | Release of Holdback (Phased)
2 | Monday | 0 |  |  |  | Prince Edward Island |  |  |  | Deemed Completion
3 | Tuesday | 0 |  |  |  | Newfoundland |  |  |  | Completion
4 | Wednesday | 0 |  |  |  | Yukon |  |  |  | Achevement substantiel de l'ouvrage
5 | Thursday | 0 |  |  |  | Nunavut
6 | Friday | 0 |  |  |  | Northwest Territory
7 | Saturday | 2 | [7 empty] | Deemed Completion
|  |  | GST | 5%
|  |  | QST | 9.5%
|  |  | QST_Blended | 14.98%
The information in this table must be manually updated to reflect any changes in the applicable lien legislation or tax rates.
The information was valid when first entered, but must be confirmed in each jurisdiction prior to use for that jurisdiction.
[8 empty] | Calculation of Basic Holdback | [5 empty] | Calculation of Substantial Performance | [5 empty] | Release of Basic Holdback |  | Calculation of Finishing Holdback |  |  |  | Release of Finishing Holdback
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Province/Territory | Location Selected | Prov Tax Type | Prov Tax Rate | VAT Tax Type | VAT Tax Rate | Tax Rate | Basic Holdback % | % | Change of Rate Threshold | % | Minimum Holdback @ Rate Change | Lien Period | % | Limit | % | Limit | % |  | Lien Period Trigger | Document Issued/Status Achieved | Finishing Holdback | Finishing Lien Period | % | Limit of Outstanding Work | Lien Period Trigger |  |  |  | Legislation | Comments
Selected: | Ontario | X | 0 | 0% | HST | 13% | 13% | 10% | 0% | 0 | 100% | 0 | 60 | 3% | 1000000 | 2% | 1000000 | 1% | 0 | Date of Publication | Certificate of Substantial Performance | 10% | 60 | 1% | 5000 | Deemed Completion | Finishing Holdback | Substantially Performed | Deemed Complete | Construction Act, Ontario | 0
5 CLA | Ontario |  |  |  | HST | 13% | 13% | 10% |  |  | 100% |  | 45 | 3% | 500000 | 2% | 500000 | 1% |  | Date of Publication | Certificate of Substantial Performance | 10% | 45 | 1% | 1000 | Deemed Completion | Finishing Holdback | Substantially Performed | Deemed Complete | Construction Lien Act, Ontario
5 CA | Ontario | X |  |  | HST | 13% | 13% | 10% |  |  | 100% |  | 60 | 3% | 1000000 | 2% | 1000000 | 1% |  | Date of Publication | Certificate of Substantial Performance | 10% | 60 | 1% | 5000 | Deemed Completion | Finishing Holdback | Substantially Performed | Deemed Complete | Construction Act, Ontario
6 | Quebec |  | QST | 9.5% | GST | 5% | 14.98% | 10% |  |  | 100% |  | 30 | 3% | 500000 | 2% | 500000 | 1% |  | Date of Issuance | Certificat d'achevement substantiel de l'ouvrage | 10% | 30 | 1% | 1000 | Deemed Completion | Finishing Holdback | Substantially Performed | Deemed Complete | Civil Code Quebec article 2727 | based on common practice
1 | British Columbia |  |  |  | GST | 5% | 5% | 10% |  |  | 100% |  | 55 | 0 | 0 | 0 | 0 | 0 |  | Date of Issuance | Certificate of Completion | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Completed |  | Builders Lien Act, BC
2 | Alberta |  |  |  | GST | 5% | 5% | 10% |  |  | 100% |  | 45 | 3% | 500000 | 2% | 500000 | 1% |  | Date of Issuance | Certificate of Substantial Performance | 10% | 45 | 0% | 0 | Completion | Finishing Holdback | Substantially Performed | Complete | Builder's Lien Act, Alberta
3 | Saskatchewan |  |  |  | GST | 5% | 5% | 10% |  |  | 100% |  | 40 | 3% | 500000 | 2% | 500000 | 1% |  | Date of Issuance | Certificate of Substantial Performance | 10% | 40 | 1% | 1000 | Deemed Completion | Finishing Holdback | Substantially Performed | Deemed Complete | Builders Lien Act, Saskatchewan
4 | Manitoba |  |  |  | GST | 5% | 5% | 7.5% |  |  | 100% |  | 40 | 3% | 250000 | 2% | 250000 | 1% |  | Date of Issuance | Certificate of Substantial Performance | 7.5% | 40 | 0% | 0 | Completion | Finishing Holdback | Substantially Performed | Complete | The Builders' Liens Act, Manitoba
7 | New Brunswick |  |  |  | HST | 13% | 13% | 20% | 20% | 15000 | 15% | 3000 | 60 | 0 | 0 | 0 | 0 | 0 |  | Date of Issuance | Certificate of Completion | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Completed |  | Mechanics' Lien Act, New Brunswick | $3,000 min or 20% if contract is < $15,000.00
8 | Nova Scotia |  |  |  | HST | 15% | 15% | 10% |  |  | 100% |  | 60 | 2.5% | 500000 | 2.5% | 500000 | 2.5% |  | Date of Issuance | Certificate of Substantial Performance | 2.5% | 60 | 0% | 0 | Completion | Finishing Holdback | Substantially Performed | Complete | Builders Lien Act, Nova Scotia | Finishing holdback is 2.5% of work done, not of work remaining
9 | Prince Edward Island |  |  |  | HST | 14% | 14% | 20% | 20% | 15000 | 15% | 3000 | 60 | 0 | 0 | 0 | 0 | 0 |  | Date of Issuance | Certificate of Completion | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Substantially Performed |  | Mechanics' Lien Act, P.E.I. | $3,000 min or 20% if contract is < $15,000.00
10 | Newfoundland |  |  |  | HST | 13% | 13% | 10% |  |  | 100% |  | 30 | 3% | 250000 | 2% | 250000 | 1% |  | Date of Issuance | Certificate of Substantial Performance | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Substantially Performed |  | Mechanics' Lien Act, Newfoundland
11 | Yukon |  |  |  | GST | 5% | 5% | 10% |  |  | 100% |  | 30 | 0 | 0 | 0 | 0 | 0 |  | Date of Achievement | Completion | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Completed |  | Lien Act, Yukon
12 | Nunavut |  |  |  | GST | 5% | 5% | 10% |  |  | 100% |  | 45 | 0 | 0 | 0 | 0 | 0 |  | Date of Achievement | Completion | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Completed |  | Mechanics Lien, Nunavut
13 | Northwest Territory |  |  |  | GST | 5% | 5% | 10% |  |  | 100% |  | 45 | 0 | 0 | 0 | 0 | 0 |  | Date of Achievement | Completion | 0% | 0 | 0% | 0 | No Finishing Holdback | Holdback | Completed |  | Lien Act, NWT
Insert above this row
| Completed to date calculation for NB & PEI due to sliding scale of holdback percentages | [6 empty] | 0
|  | Sheet name | Cert # | Named range |  |  | Concatenation of cell address | [7 empty] | NB | PEI
| Schedule of Values- | App For Payment- | 01 | '!WorkFinished |  | 'App For Payment-01'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 02 |  |  | 'App For Payment-02'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 03 |  |  | 'App For Payment-03'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 04 |  |  | 'App For Payment-04'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 05 |  |  | 'App For Payment-05'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 06 |  |  | 'App For Payment-06'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 07 |  |  | 'App For Payment-07'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 08 |  |  | 'App For Payment-08'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 09 |  |  | 'App For Payment-09'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 10 |  |  | 'App For Payment-10'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 11 |  |  | 'App For Payment-11'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 12 |  |  | 'App For Payment-12'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 13 |  |  | 'App For Payment-13'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 14 |  |  | 'App For Payment-14'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 15 |  |  | 'App For Payment-15'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 16 |  |  | 'App For Payment-16'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 17 |  |  | 'App For Payment-17'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 18 |  |  | 'App For Payment-18'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 19 |  |  | 'App For Payment-19'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 20 |  |  | 'App For Payment-20'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 21 |  |  | 'App For Payment-21'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 22 |  |  | 'App For Payment-22'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 23 |  |  | 'App For Payment-23'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 24 |  |  | 'App For Payment-24'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 25 |  |  | 'App For Payment-25'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 26 |  |  | 'App For Payment-26'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 27 |  |  | 'App For Payment-27'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 28 |  |  | 'App For Payment-28'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 29 |  |  | 'App For Payment-29'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 30 |  |  | 'App For Payment-30'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 31 |  |  | 'App For Payment-31'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 32 |  |  | 'App For Payment-32'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 33 |  |  | 'App For Payment-33'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 34 |  |  | 'App For Payment-34'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 35 |  |  | 'App For Payment-35'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 36 |  |  | 'App For Payment-36'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 37 |  |  | 'App For Payment-37'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 38 |  |  | 'App For Payment-38'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 39 |  |  | 'App For Payment-39'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 40 |  |  | 'App For Payment-40'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 41 |  |  | 'App For Payment-41'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 42 |  |  | 'App For Payment-42'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 43 |  |  | 'App For Payment-43'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 44 |  |  | 'App For Payment-44'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 45 |  |  | 'App For Payment-45'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 46 |  |  | 'App For Payment-46'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 47 |  |  | 'App For Payment-47'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 48 |  |  | 'App For Payment-48'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 49 |  |  | 'App For Payment-49'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 50 |  |  | 'App For Payment-50'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 51 |  |  | 'App For Payment-51'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%
|  |  | 52 |  |  | 'App For Payment-52'!WorkFinished | [5 empty] | #REF! |  | 0 | 20% | 20%

## Sheet1 (hidden)
DOW | Name | Add to skip weekend
1 | Sunday | 1
2 | Monday | 0
3 | Tuesday | 0
4 | Wednesday | 0
5 | Thursday | 0
6 | Friday | 0
7 | Saturday | 2