## Sheet1
Project Name: | Jone's Room Addition |  |  | Date: |  | Walk through date
|  |  |  | Payment #: |  | #?
Owner: | Your name
Contractor: | Their name |  |  | Form courtesy of
Task # | Task Name | Assigned Value | Previously Paid | Pay This Now | % approved | Balance Owed
1 | Demolition | 3000 | 1500 | 1500 | 100% | 0
2 | Concrete | 5000 | 2000 | 3000 | 100% | 0
3 | Framing | 8000 | 0 | 4000 | 50% | 4000
4 | Steel | 1500 | 0 | 750 | 50% | 750
5 | Plumbing | 3000 | 0 | 600 | 20% | 2400
6 | Electrical | 3000 | 0 | 600 | 20% | 2400
7 | Mechanical | 2500 | 0 | 0 | 0% | 2500
8 | Insulation | 1500 | 0 | 0 | 0% | 1500
9 | Roofing | 3000 | 0 | 0 | 0% | 3000
10 | Doors & Windows | 3000 | 0 | 0 | 0% | 3000
11 | Exterior covering | 2000 | 0 | 0 | 0% | 2000
12 | Drywall | 4000 | 0 | 0 | 0% | 4000
13 | Finish Carpentry | 4000 | 0 | 0 | 0% | 4000
14 | Casework | 3000 | 0 | 0 | 0% | 3000
15 | Paint | 3500 | 0 | 0 | 0% | 3500
16 | Flooring | 5000 | 0 | 0 | 0% | 5000
17 | Ladscape | 2000 | 0 | 0 | 0% | 2000
18 | Clean up | 800 | 0 | 0 | 0% | 800
19 | Other | 0 | 0 | 0 | 0% | 0
20 | Other | 0 | 0 | 0 | 0% | 0
| TOTAL | 57800 | 3500 | 10450 | 17% | 43850
I agreee that the current payment alocated represents an accurate progress payment on the project.
| Owner |  |  | Contractor
| Date |  |  | Date
Note on F8: Enter percentage of completion. Form will adjust automatically.
Note on C28: Total project amount
Note on D28: Already paid before
Note on E28: Payment due this time.
Note on G28: Balance owed on total project amount. (remember 10% retention)